## angel-investor-engagemen
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=angel-investor-engagement
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Market Research
Define Research Objective
Identify Target Market
Data Collection Planning
Conduct Interviews
Send Out Surveys
Competitor Analysis
Industry Trends Study
SWOT Analysis
Analyze Collected Data
Interpret Findings
Draft Research Report
Finalize Research Report
Business Model Development
Identify Value Proposition
Determine Key Activities
Define Key Resources
Establish Key Partnerships
Identify Customer Segments
Establish Channels
Create Customer Relationships
Formulate Revenue Streams
Set Cost Structure
Construct Business Model Canvas
Validate Business Model
Revise and Finalize Business Model
Financial Analysis
Define Financial Goals
Gather Financial Data
Conduct Revenue Forecasting
Analyze Cost Structure
Calculate Gross Profit Margin
Run Break-Even Analysis
Create Cash Flow Statement
Perform Net Present Value Analysis
Conduct Risk Assessment
Draw Financial Projections
Review and Interpret Results
Finalize Financial Report
Investor Prospecting
Define Investor Persona
Research Potential Investors
Create Investor List
Develop Investor Profiles
Prioritize Prospects
Develop Outreach Strategy
Customize Investment Proposal
Plan Meeting Schedules
First Contact
Follow-up Communications
Build Investor Relationships
Maintain Investor Database
Pitch Deck Creation
Define Pitch Goals
Plan Presentation Structure
Create Draft Outline
Develop Problem Statement
Present Solution Proposal
Showcase Market Analysis
Detail Business Model
Highlight Team Composition
Prepare Financial Projections
Finalize Investment Ask
Rehearse Pitch Delivery
Refine and Finalize Deck
Outreach and Networking
Develop Networking Strategy
Identify Networking Events
Prepare Elevator Pitch
Create Business Cards
Attend Networking Events
Meet Potential Investors
Establish Contact with Key Players
Follow up on Leads
Arrange Business Meetings
Build Strategic Partnerships
Maintain Ongoing Communication
Expand Network.
Pitching to Investors
Schedule Investor Meeting
Prepare Presentation Materials
Rehearse Pitch Delivery
Deliver Pitch Presentation
Address Investor Queries
Discuss Business Plan
Share Financial Projections
Highlight Potential Returns
Offer Investment Opportunities
Collect Investor Feedback
Follow up Post-Pitch
Refine Pitch Based on Feedback
Negotiating Terms
Understand Investment Needs
Prepare Negotiation Strategy
Set Initial Terms
Present Terms to Investors
Listen to Investor's Concerns
Discuss and Clarify Terms
Negotiate Deal Structure
Negotiate Valuation
Agree on Exit Strategy
Finalize Investment Terms
Draft Term Sheet
Sign Term Sheet
Securing Investment
Legal Due Diligence
Financial Due Diligence
Prepare Investment Agreement
Review Investment Agreement
Negotiate Final Amendments
Sign Investment Agreement
Receive Investment Funds
Update Company Records
Notify Stakeholders
Implement Changes per Agreement
Manage Investor Relations
Regular Reporting to Investors
Post-Investment Management
Develop Post-Investment Plan
Implement Business Model Changes
Hire New Team Members
Update Business Operations
Begin Growth Initiatives
Regular Investor Updates
Financial Reporting
Manage Investor Relations
Conduct Performance Review
Address Investor Concerns
Plan for Next Funding Round
Prepare for Exit Strategy