## Anniversary Celebratio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=anniversary-celebration
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Defining Objectives
Gathering Team Members
Understanding Client Needs
Researching Event Themes
Establishing Timeframes
Outlining Scope of Project
Identifying Risks
Drafting Initial Project Plan
Setting Up Communication Channels
Preparing Documentation
Securing Initial Approvals
Initiating Project Kick-off Meeting
Budget Planning
Identification of Expenditure Areas
Cost Estimation for Venue
Cost Estimation for Catering
Cost Estimation for Entertainment
Cost Estimation for Decorations
Cost Estimation for Invitations
Projected Miscellaneous Expenses
Drafting Preliminary Budget
Budget Review and Adjustments
Final Budget Approval
Setting Up Financial Tracking System
Establishing Contingency Plan
Venue Selection
Identifying Venue Requirements
Researching Potential Venues
Shortlisting Venues
Contacting Venue Representatives
Arranging Site Visits
Evaluating Venue Capacities
Checking Venue Availability
Comparing Venue Costs
Assessing Venue Accessibility
Reviewing Venue Contracts
Making Venue Decision
Confirming Venue Booking
Guest List Compilation
Identifying Guest Criteria
Gathering Initial Guest Names
Confirming Guest Contact Details
Categorizing Guest Importance
Assessing Venue Capacity With List
Making Necessary Guest List Adjustments
Reviewing Guest List With Client
Finalizing Guest List
Creating Guest Database
Preparing Guest Accommodation Requirements
Organizing Guest Transportation Needs
Backup Plan For Guest Cancellations
Invitation Design & Distribution
Identifying Invitation Specifications
Selecting Invitation Design Theme
Drafting Invitation Text
Reviewing & Finalizing Design
Sourcing Invitation Production
Proofing & Approving Final Sample
Producing Invitations
Preparing Invitation Package
Compiling Delivery Addresses
Distributing Invitations Physically
Sending Digital Invitations
Tracking Invitation Responses
Catering & Entertainment Arrangement
Identifying Dietary Preferences
Listing Potential Caterers
Tasting Sessions with Caterers
Finalizing Caterer Selection
Designing Menu
Confirming Catering Order
Identifying Entertainment Needs
Researching Entertainment Options
Auditioning/Interviewing Entertainers
Finalizing Entertainment Selection
Scheduling Entertainment Program
Confirming Entertainment Booking
Event Decor Planning
Identifying Decor Theme
Sketching Decor Layout
Listing Required Decor Items
Sourcing Decor Suppliers
Reviewing Decor Samples
Finalizing Decor Selection
Confirming Decor Order
Coordinating Decor Delivery
Planning Decor Setup
Supervising Decor Installation
Final Decor Inspection
Adjusting Decor If Necessary
Anniversary Program Design
Identifying Event Segments
Drafting Event Timeline
Sequencing Event Activities
Incorporating Entertainment Acts
Designating Speeches & Toasts
Planning Anniversary Highlights
Scheduling Breaks & Intermissions
Reviewing Program Flow
Finalizing Program Schedule
Designing Event Program Materials
Printing Event Program Materials
Distributing Program Materials to Staff
Event Execution
Setting Up Venue
Installing Decorations
Final Venue Inspection
Staff Briefing
Welcoming Guests
Managing Seating Arrangements
Overseeing Catering and Entertainment
Coordinating Event Timeline
Handling Guest Requests/Issues
Supervising Event Activities
Facilitating Event Closure
Venue Clean-up and Breakdown
Post-Event Evaluation
Gathering Feedback Forms
Conducting Staff Debrief
Assessing Guest Satisfaction
Reviewing Event Objectives
Evaluating Budget Utilization
Assessing Venue Performance
Reviewing Catering and Entertainment Effectiveness
Analyzing Decor Impact
Assessing Response to Program Design
Evaluating Event Execution Success
Compiling Post-Event Report
Presenting Evaluation Results to Client