## Bathroom Makeove
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=bathroom-makeover
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Planning
Initial Consultation
Needs Assessment
Design Ideas
Preliminary Sketches
Space Measurements
Detailed Design Development
Material Procurement Planning
Timeline Establishment
Legal Permits Review
Contractor Selection
Final Plan Approval
Pre-construction Meeting
Budget Setting
Financial Assessment
Project Scope Definition
Cost Estimation
Material Costing
Labor Cost Analysis
Permit and Fees Calculation
Contingency Planning
Budget Drafting
Budget Review
Budget Adjustments
Final Budget Approval
Budget Documentation
Material Selection
Functionality Assessment
Design Style Decision
Material Research
Vendor Comparison
Material Sampling
Durability Consideration
Cost-effectiveness Analysis
Environmental Impact Assessment
Material Shortlisting
Final Material Selection
Order Placement
Delivery Arrangement
Demolition Phase
Safety Measures Planning
Protective Gear Distribution
Utility Disconnection
Site Preparation
Fixture Removal
Wall and Floor Demolition
Plumbing and Electrical Dismantling
Debris Collection
Material Recycling
Debris Disposal
Site Cleaning
Post-Demolition Inspection
Plumbing Overhaul
Plumbing Plan Review
Existing Plumbing Evaluation
Required Equipment List
Plumbing Equipment Purchase
Old Pipe Removal
New Pipe Installation
Drainage System Setup
Fixture Attachment Preparation
Water Heater Installation
Leak Test Conducting
System Inspection
Cleanup and Finalization
Electrical Updates
Electrical System Evaluation
New Layout Plans
Wiring Material Procurement
Safety Preparations
Old Wiring Removal
New Wiring Installation
Outlet and Switches Setup
Light Fixture Installation
Ventilation System Wiring
Circuit Testing
Safety Inspection
System Documentation
Wall and Floor Installation
Surface Preparation
Material Delivery
Wall Insulation Installation
Drywall Setup
Wall Finishing
Wall Painting or Wallpapering
Underlayment Placement
Floor Material Laying
Flooring Adhesion or Nailing
Flooring Finishing
Grouting and Sealing
Final Inspection and Cleanup
Fixtures Installation
Fixture Delivery Check
Installation Planning
Safety Preparations
Fixture Placement
Plumbing Connection
Electrical Connection
Fixture Securing
Sealant Application
Fixture Testing
Fixture Adjustment
Cleanup After Installation
Final Inspection
Finishing Touches
Detailed Inspection
Minor Adjustments
Paint Touch-ups
Fixture Polishing
Grout Cleaning
Floor Polishing
Decor Installation
Lighting Adjustment
Ventilation Check
Safety Inspection
Functionality Testing
Final Clean-up
Cleanup and Review
Debris Collection
Material Recycling
Trash Disposal
Cleaning Equipment Gathering
Surface Cleaning
Dusting and Vacuuming
Window Cleaning
Ventilation System Check
Final Walk-through
Customer Feedback Collection
Project Documentation Finalization
Project Closure