## Benefit Concer
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=benefit-concert
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Concept Initiation
Identifying Objectives
Assembling Team
Defining Theme
Project Scope Determination
Risk Assessment
Proposal Writing
Setting Deadlines
Preliminary Budget Estimation
Market Research
Stakeholder Identification
Concept Presentation
Approval Seeking
Budget Planning
Budget Objective Identification
Revenue Estimation
Expense Forecasting
Contingency Planning
Resource Allocation
Financial Risk Analysis
Budget Drafting
Budget Review
Budget Adjustment
Final Budget Approval
Budget Documentation
Budget Communication
Venue Selection
Venue Requirement Identification
Venue Search Initiation
Potential Venue Evaluation
Site Visits
Venue Cost Analysis
Venue Availability Check
Capacity Assessment
Facility Inspection
Venue Contract Review
Negotiation with Venue Owner
Contract Signing
Venue Booking Confirmation
Artist Recruitment
Artist Requirement Identification
Talent Search Initiation
Potential Artist Evaluation
Contacting Agents/Artists
Artist Availability Check
Fee Negotiation
Contract Review with Artists
Contract Signing with Artists
Artist Booking Confirmation
Performance Schedule Creation
Artistic Requirements Gathering
Artist Communication Maintenance
Sponsor Negotiation
Identify Potential Sponsors
Sponsorship Package Creation
Initial Sponsor Contact
Sponsor Meeting Arrangement
Sponsorship Proposal Presentation
Sponsorship Benefits Discussion
Contract Terms Negotiation
Sponsorship Contract Review
Contract Signing with Sponsors
Sponsorship Confirmation
Sponsor Branding Plan Creation
Regular Sponsor Communication
Marketing Strategy
Market Analysis
Target Audience Identification
Marketing Objective Setting
Creating Promotional Mix
Budget Allocation for Marketing
Marketing Channels Selection
Marketing Content Creation
Marketing Schedule Planning
Marketing Campaign Launch
Marketing Performance Tracking
Marketing Adjustments and Optimization
Post-Event Marketing Analysis
Ticket Sales
Pricing Strategy Development
Ticket Category Determination
Ticket Sales Platform Selection
Ticketing System Setup
Sales Launch Announcement
Initial Ticket Release
Sales Monitoring
Promotional Sales Implementation
Ticket Sales Reporting
Last Call Sales Push
Final Sales Tally
Post-Sale Analysis
Event Organization
Event Timeline Creation
Staff Recruitment and Training
Equipment Sourcing
Supplier Negotiation
Production Schedule Development
Venue Layout Plan
Security Arrangement
Catering Arrangement
Transportation Logistics
Rehearsal Management
Set-up and Decoration
Final Event Check
Concert Execution
Team Briefing
Venue Preparation Check
Artist Arrival Management
Staff and Volunteer Coordination
Guest Entry Management
Concert Start Execution
On-site Problem Solving
Crowd Management
Artist Performance Management
Emergency Response
Concert Closing Procedure
Venue Clearing and Cleanup
Post-Event Evaluation
Immediate Debrief Meeting
Feedback Collection
Financial Reconciliation
Performance Analysis
Public Response Evaluation
Sponsor Feedback Review
Artist Feedback Review
Staff and Volunteer Feedback Review
Event Report Compilation
Lessons Learned Documentation
Acknowledgment and Thank You Notes
Future Planning Discussions