## Birthday Celebratio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=birthday-celebration
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Theme Selection
Brainstorming Ideas
Researching Trends
Evaluating Options
Attaining Client's Preferences
Shortlisting Themes
Cost Estimation
Finalizing Theme
Sketching Design Elements
Matching Colors
Reviewing Theme Elements
Procuring Theme Materials
Mock-up Creation
Budget Planning
Defining Financial Limit
Identifying Expense Categories
Conducting Market Research
Estimating Individual Costs
Prioritizing Expenses
Allocating Funds
Reviewing Estimates
Making Budget Adjustments
Finalizing Budget
Documenting Detailed Plan
Setting up Contingency Fund
Approval from Stakeholders
Guest List Creation
Outlining Guest Categories
Identifying Key Attendees
Collecting Guest Details
Making Preliminary List
Checking Venue Capacity
Adjusting List as Per Capacity
Marking VIP Guests
Considering Inviter's Preferences
Finalizing Guest List
Alphabetizing for Ease
Creating Backup List
Saving and Sharing List
Venue Booking
Identifying Venue Requirements
Conducting Venue Search
Shortlisting Potential Venues
Scheduling Site Visits
Evaluating Venue Facilities
Checking Venue Availability
Negotiating Rental Price
Reviewing Venue Contract
Finalizing Venue Selection
Making Booking Deposit
Confirming Venue Reservation
Documenting Venue Details
Invitations Design and Distribution
Drafting Invitation Contents
Conceptualizing Design
Selecting Color Scheme
Creating Design Mock-ups
Incorporating Event Details
Finalizing Invitation Design
Printing Invitations
Enveloping and Addressing
Acquiring Postage
Mailing Physical Invitations
Digitally Distributing Invitations
Tracking RSVPs
Menu and Cake Decisions
Identifying Dietary Restrictions
Brainstorming Menu Ideas
Selecting Course Categories
Consulting with Caterer
Sampling Dishes
Finalizing Menu Items
Deciding Cake Flavor
Designing Cake Appearance
Approving Cake Design
Placing Catering Order
Confirming Delivery Details
Arranging Food Tasting
Entertainment Arrangement
Identifying Entertainment Needs
Researching Entertainment Options
Shortlisting Entertainers
Contacting Potential Entertainers
Negotiating Performance Fees
Checking Availability
Booking Selected Entertainment
Confirming Schedule
Arranging Equipment
Rehearsing Performance
Coordinating Event Day Details
Confirming Payment Details
Decorations Procurement
Identifying Decoration Needs
Selecting Decoration Theme
Sketching Layout Design
Creating Shopping List
Sourcing Decoration Suppliers
Comparing Prices
Placing Orders
Confirming Delivery Dates
Receiving Decorations
Checking Order Accuracy
Storing Decorations Safely
Arranging for Installation
Event Execution
Setting Timeline
Organizing Staff Briefing
Coordinating Setup
Checking Venue Preparation
Overseeing Decoration Installation
Arranging Food and Beverage Stations
Directing Entertainment Rehearsals
Reviewing Event Layout
Welcoming Guests
Managing Event Flow
Solving on-site Problems
Closing Event Properly
After Party Cleanup
Assigning Cleanup Tasks
Disassembling Decorations
Packing Up Unused Supplies
Clearing Food and Beverage Areas
Cleaning Guest Areas
Removing Trash
Checking Lost and Found
Inspecting Venue for Damages
Returning Rented Equipment
Securing Leftover Items
Finalizing Venue Cleaning
Completing Venue Handover