## Brand Perception Surve
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=brand-perception-survey
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Inception
Project Briefing
Team Formation
Goal Setting
Budget Estimation
Scope Definition
Timeline Creation
Resource Allocation
Responsibility Assignment
Strategic Planning
Risk Identification
Communication Plan Development
Project Kick-off Meeting
Market Research
Research Design
Target Market Definition
Data Source Identification
Research Method Selection
Data Collection Tool Development
Sample Size Determination
Data Collection Training
Fieldwork Execution
Primary Data Gathering
Secondary Data Exploration
Data Organizing
Preliminary Data Review
Questionnaire Development
Objective Clarification
Questionnaire Type Selection
Question Formation
Response Format Design
Question Sequencing
Pilot Questionnaire Creation
Pilot Testing
Feedback Collection
Questionnaire Revision
Final Questionnaire Formation
Questionnaire Validation
Questionnaire Finalization
Participant Selection
Participant Criteria Definition
Initial Database Compilation
Database Screening
Potential Participant Identification
Random Sampling
Eligibility Verification
Invitation Drafting
Invitation Distribution
Response Tracking
Participant Confirmation
Consent Obtaining
Participant List Finalization
Survey Distribution
Distribution Strategy Planning
Distribution Channel Selection
Survey Packaging
Survey Announcement Preparing
Announcement Dissemination
Survey Dispatching
Tracking Code Assignment
Delivery Confirmation
Non-Response Follow-up
Reminder Sending
Response Monitoring
Survey Closure Notification
Response Collection
Response Reception Setup
Response Tracking System Activation
Initial Response Collection
Ongoing Response Monitoring
Non-Response Handling
Query Management
Response Validity Checking
Duplicate Response Removal
Incomplete Response Follow-up
Final Response Gathering
Response Collection Closure
Response Data Backup
Data Analysis
Data Cleaning
Data Preparation
Variable Identification
Univariate Analysis
Bivariate Analysis
Multivariate Analysis
Data Interpretation
Statistical Testing
Hypothesis Evaluation
Data Visualization
Analysis Summary
Data Storage and Archiving
Insight Generation
Analysis Review
Key Findings Identification
Insight Extraction
Insight Validation
Pattern Recognition
Trend Analysis
Insight Categorization
Insight Prioritization
Implication Assessment
Strategic Recommendations
Insight Documentation
Insight Presentation Preparation
Report Compilation
Report Structure Design
Introduction Writing
Methodology Explanation
Data Presentation
Findings Description
Insights Integration
Recommendations Formulation
Conclusion Summarizing
Appendices Preparation
Source Citation
Report Review and Editing
Final Report Production
Result Presentation
Presentation Outline Creation
Slide Designing
Data Visualization Incorporation
Key Points Highlighting
Speaking Notes Preparation
Rehearsal and Timing
Feedback Incorporation
Presentation Finalizing
Meeting Scheduling
Audience Preparation
Presentation Delivery
Question and Answer Session