## Bungalo
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=bungalow
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Concept Development
Client Briefing
Budget Estimation
Market Research
Idea Generation
Environmental Impact Analysis
Feasibility Study
Concept Visualization
Preliminary Designs
Client Feedback
Concept Refinement
Final Concept Approval
Documentation of Concept.
Site Analysis
Site Visit
Location Mapping
Geographical Assessment
Climate Study
Soil Testing
Assessment of Surroundings
Accessibility Analysis
Utility Assessment
Sun Path Study
Noise Level Analysis
Site Data Compilation
Site Analysis Report Preparation
Design Process
Brainstorming Sessions
Sketching Initial Ideas
Drafting Floor Plans
Designing Elevations
Creating 3D Models
Material Selection
Lighting Design
Landscape Planning
Integration of Utilities
Design Review
Client Approval
Final Design Documentation
Planning Permissions
Understanding Local Regulations
Gathering Required Documents
Preparing Application
Drafting Site Plans
Incorporating Project Specifications
Filing Building Consent
Communicating with Authorities
Addressing Queries
Making Necessary Revisions
Final Submission
Awaiting Permission Decision
Obtaining Planning Permissions
Construction Drawings
Drafting Foundation Plans
Designing Floor Layouts
Creating Elevation Drawings
Drafting Sectional Views
Detailing Structural Elements
Designing Electrical Layout
Plumbing Layout Drawings
Creating Heating, Ventilation, and Air Conditioning (HVAC) Plans
Landscape Design Drawings
Creating Detailed Specifications
Reviewing and Revising Drawings
Finalizing Construction Drawings
Contractor Selection
Defining Contractor Requirements
Advertising Tender
Receiving Bids
Reviewing Proposals
Checking Contractor Credentials
Assessing Past Projects
Interviewing Potential Contractors
Evaluating Pricing and Availability
Checking References
Negotiating Contract Terms
Finalizing Contractor Selection
Contract Signing
Construction Phase
Site Preparation
Foundation Construction
Building Framework
Installing Utilities and Services
Wall and Roof Construction
Window and Door Installation
Interior Finishing
Installation of Heating, Ventilation, and Air Conditioning (HVAC)
Painting and Decorating
Landscaping
Final Inspection
Addressing Punch List Items
Project Monitoring
Establishing Monitoring Plan
Regular Site Visits
Quality Checks
Progress Reporting
Budget Tracking
Schedule Tracking
Handling Change Requests
Risk Assessment
Safety Inspections
Coordinating with Contractors
Addressing Issues
Documentation of Monitoring Results.
Finishing Phase
Final Interior Work
Electrical Fittings
Plumbing Fixtures Installation
Flooring Installation
Wall Finishing
Paint Touch-ups
Installation of Appliances
Exterior Finishing
Lighting Setup
Cleaning and Debris Removal
Final Quality Check
Preparation for Handover
Project Handover
Final Inspection
Addressing Any Last-Minute Fixes
Assembling Handover Documents
Preparing Warranty Information
Organizing User Manuals
Conducting Final Clean-Up
Scheduling Handover Meeting
Walking Client Through the Project
Explaining Maintenance Procedures
Handling Over Keys
Obtaining Client Sign-off
Post-Handover Support Briefing