## Charity Gala or Dinne
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=charity-gala-diner
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Concept Development
Project Initiation
Charity Cause Identification
Gala Theme Selection
Setting Objectives
Identifying Key Stakeholders
Forming the Organizing Team
Developing the Event Format
Creating a Preliminary Timeline
Drafting the Project Plan
Goal Setting for Fundraising
Planning Communication Strategy
Finalizing the Concept Proposal
Budget Planning
Identifying Funding Sources
Estimating Revenue
Projecting Attendance
Calculating Venue Costs
Estimating Food and Beverage Expenses
Determining Entertainment Costs
Factoring in Decor Expenses
Budgeting for Invitations and Marketing
Allocating Funds for Staffing
Setting Aside Contingency Funds
Reviewing and Adjusting the Budget
Finalizing the Financial Plan
Venue Selection
Requirement Identification
Potential Venue Research
Site Visits
Capacity Assessment
Accessibility Evaluation
Technical Facilities Review
Cost Analysis
Availability Check
Venue Comparison
Contract Negotiation
Venue Booking
Confirmation of Venue Details
Date and Time Scheduling
Determining Event Length
Checking Calendar for Clashes
Assessing Seasonal Factors
Acknowledging Major Holidays
Evaluating Potential Dates
Consulting Key Participants
Setting Primary and Alternate Dates
Establishing Start and End Times
Considering Time Zones for Virtual Participation
Finalizing Event Date and Time
Communicating Date to Relevant Parties
Incorporating Date into Promotional Materials
Guest List Compilation
Identifying Target Audience
Compiling Potential Guest Names
Checking Previous Attendee Lists
Adding Key Stakeholders
Including Potential Donors
Considering Guest Plus-Ones
Reviewing Guest List Size
Prioritizing Invitations
Creating a Waitlist
Finalizing the Guest List
Preparing Contact Information
Segregating VIPs and Special Attendees
Invitations and RSVPs
Designing Invitations
Finalizing Invitation Wording
Including Necessary Details
Printing Physical Invitations
Emailing Digital Invitations
Mailing Physical Invitations
Sending Invitation Reminders
Setting RSVP Deadline
Tracking Received RSVPs
Following Up on Pending RSVPs
Updating Guest List
Preparing Final Attendance List
Menu and Decor Planning
Identifying Dietary Preferences
Selecting Meal Types
Creating Menu Options
Sampling Food and Beverage
Finalizing Menu
Determining Decor Theme
Sketching Decor Layout
Sourcing Decor Suppliers
Comparing Decor Quotes
Ordering Decor Items
Confirming Delivery Dates
Finalizing Decor Plan
Entertainment Arrangement
Identifying Entertainment Needs
Brainstorming Entertainment Ideas
Researching Potential Performers
Contacting Entertainment Agencies
Comparing Talent Fees
Selecting Performers
Creating Entertainment Schedule
Signing Entertainment Contracts
Coordinating Technical Requirements
Arranging Rehearsals
Confirming Transportation and Accommodation
Finalizing Entertainment Details
Event Execution
Setting Up Venue
Arranging Decorations
Preparing Food and Beverage
Checking Audio-Visual Equipment
Briefing Staff Members
Receiving Guests
Managing Event Flow
Supervising Entertainment Performances
Facilitating Donations
Ensuring Guest Satisfaction
Handling Unexpected Issues
Closing the Event
Post-Event Follow-up
Clearing the Venue
Settling Outstanding Payments
Distributing Thank You Notes
Collecting Feedback
Evaluating Event Success
Analyzing Financial Performance
Documenting Lessons Learned
Updating Donor Database
Reporting to Stakeholders
Conducting Debrief Meeting
Planning for Future Events
Archiving Event Data