## city-park-developmen
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=city-park-development
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Define Objectives
Identify Stakeholders
Outline Scope
Project Kick-off Meeting
Establish Team Roles
Draft Initial Budget
Develop Project Timeline
Assess Risk Factors
Create Communication Plan
Prepare Project Charter
Secure Initial Resources
Obtain Project Approval
Site Analysis
Define Analysis Objectives
Assemble Analysis Team
Perform Initial Site Visit
Collect Site Data
Conduct Soil Testing
Evaluate Environmental Impact
Assess Surrounding Infrastructure
Analyze Local Regulations
Review Historical Data
Conduct Traffic and Accessibility Study
Compile Site Analysis Report
Review and Finalize Report
Concept Development
Define Conceptual Goals
Brainstorm Design Ideas
Sketch Preliminary Concepts
Conduct Feasibility Studies
Create Digital Renderings
Present Initial Proposals
Gather Stakeholder Feedback
Refine Design Concepts
Develop Scale Models
Evaluate Sustainability Options
Finalize Concept Design
Prepare Concept Presentation
Preliminary Design
Establish Design Criteria
Draft Preliminary Layout
Create Structural Plan
Design Site Features
Integrate Sustainability Solutions
Develop Preliminary Material List
Generate Cost Projections
Review Safety Considerations
Draft Design Specifications
Conduct Design Review
Incorporate Feedback
Finalize Preliminary Design
Detail Design
Define Detailed Design Objectives
Develop Detailed Drawings
Specify Material Choices
Calculate Precise Dimensions
Designate Color and Texture Options
Develop Lighting Plan
Plan Landscaping Details
Outline Drainage Solutions
Create Detailed Cost Analysis
Conduct Design Quality Check
Validate Regulatory Compliance
Finalize and Approve Detailed Design
Cost Estimation
Define Cost Estimation Objectives
Categorize Cost Elements
Identify Material Quantities
Obtain Material Costs
Calculate Labor Costs
Evaluate Equipment Expenses
Estimate Project Overheads
Include Contingency Amount
Apply Financial Analysis Methods
Review and Adjust Estimates
Finalize Initial Cost Estimation
Present and Approve Budget
Project Approval
Compile Project Documents
Conduct Pre-Approval Review
Submit Project for Approval
Answer Stakeholder Queries
Present Project to Board
Incorporate Revision Requests
Resubmit Revised Project
Obtain Initial Approvals
Secure Regulatory Approvals
Receive Final Approval Signatures
File Approved Documents
Announce Project Approval
Contract Tendering
Define Tender Requirements
Prepare Tender Documents
Publish Tender Notice
Conduct Pre-Bid Meeting
Answer Bidder Queries
Receive Bid Submissions
Review and Evaluate Bids
Shortlist Potential Contractors
Conduct Bidder Interviews
Select Preferred Contractor
Negotiate Contract Terms
Sign and Award Contract
Construction Phase
Plan Construction Schedule
Mobilize Construction Site
Begin Site Excavation
Erect Structural Framework
Install Utilities and Systems
Conduct Regular Site Inspections
Manage Construction Progress
Address Field Changes
Monitor Quality Control
Prepare for Final Inspection
Obtain Occupancy Permit
Complete Construction Clean-up
Post-Construction Review
Debrief Construction Team
Gather Project Documents
Review Project Objectives
Evaluate Project Performance
Analyze Cost Management
Assess Quality of Work
Solicit Stakeholder Feedback
Identify Lessons Learned
Record Project Successes
Document Project Challenges
Prepare Final Project Report
Present Post-Construction Review