## Commercial buildin
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=commercial-complex-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Kick-off Meeting
Stakeholder Identification
Business Case Preparation
Project Scope Definition
Setting Objectives
Team Assembly
Resource Allocation
Risk Assessment
Project Timeline Establishment
Budget Planning
Project Charter Development
Project Approval Process
Site Analysis
Site Visit Planning
Site Inspection
Topographical Study
Neighborhood Analysis
Soil Testing
Climatic Conditions Study
Regulatory Constraints Analysis
Infrastructure Assessment
Site Accessibility Evaluation
Environmental Impact Analysis
Site SWOT Analysis
Site Report Compilation
Conceptual Design
Brainstorming Sessions
Preliminary Sketching
Functional Requirements Analysis
Space Planning
Aesthetic Considerations
Preliminary Material Selection
3D Modeling
Review with Stakeholders
Design Revisions
Final Conceptual Design
Cost Estimation
Design Presentation
Detailed Design
Technical Requirements Gathering
Detailed Sketching
Structural Design
Mechanical, Electrical, and Plumbing (MEP) Design
Material Finalization
Lighting and Acoustics Design
Fire Safety Design
Detailed 3D Modeling
Integration of Design Elements
Design Documentation
Design Review and Approval
Final Detailed Design Presentation
Planning Permission
Regulatory Research
Permit Application Preparation
Compilation of Design Documents
Environmental Impact Statement
Submission of Permit Application
Liaising with Local Authorities
Public Consultation (if required)
Addressing Regulatory Queries
Modifications Based on Feedback
Resubmission of Revised Plans
Obtaining Permission Approval
Compliance Documentation.
Contractor Selection
Creation of Contractor Criteria
Market Research
Invitation to Bid
Bid Collection
Bid Assessment
Background Checks
Contractor Interviews
Reference Checks
Cost Negotiation
Contract Drafting
Contract Review
Contractor Finalization
Construction Preparation
Construction Schedule Development
Material Procurement
Site Safety Plan
Equipment Acquisition
Labor Force Planning
Site Clearance
Setting Up Temporary Facilities
Detailed Work Breakdown
Risk Management Plan
Quality Assurance Plan
Communications Plan
Construction Kick-off Meeting
Building Construction
Site Excavation
Foundation Construction
Structural Framework Setup
Roofing and Flooring Installation
Wall Construction
Electrical and Plumbing Installation
HVAC System Installation
Exterior Finishing
Interior Finishing
Landscaping
Final Inspection
Rectification Work.
Quality Control
Quality Control Plan Development
Material Inspection
Workmanship Monitoring
Compliance Checks
Regular Audit Schedules
Testing and Sampling
Issue Identification
Corrective Actions
Re-inspection
Documentation of Quality Control Processes
Final Quality Assurance Review
Quality Control Report Submission
Project Handover
Completion Certificate Obtaining
Final Walkthrough Preparation
Client Walkthrough
Punch List Creation
Defect Rectification
Final Cleaning
Handover Documentation Preparation
Operations and Maintenance Training
Final Handover Meeting
Transfer of Keys and Access
Post-Handover Support Planning
Project Closure Report.