## Competitive Market Assessmen
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=competitive-market-assessment
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Market Research Initiation
Project Objective Definition
Research Team Formation
Research Scope Identification
Research Methodology Determination
Research Tools Selection
Data Collection Criteria Setup
Training Research Team
Establishing Timeline for Research
Allocating Resources for Research
Initial Data Collection
Preliminary Data Analysis
Preparing Initial Research Report
Competition Identification
Identification of Potential Competitors
Categorization of Direct and Indirect Competitors
Building Competitor Profiles
Collection of Competitor Product Data
Analysis of Competitor Market Share
Review of Competitor Marketing Strategies
Assessment of Competitor Distribution Channels
Evaluation of Competitor Customer Relationships
Comparing Competitor Pricing Strategies
Review of Competitor Strengths and Weaknesses
Analysis of Competitor Opportunities and Threats
Finalizing Competitive Landscape Report
Competitive Analysis
Determination of Analysis Objectives
Selection of Relevant Competitors
Compilation of Competitor Data
Analysis of Competitor Products and Services
Assessment of Competitor Strengths
Identification of Competitor Weaknesses
Evaluation of Competitor Marketing Tactics
Examination of Competitor Sales Strategies
Review of Competitor Market Positioning
Comparative Financial Analysis
Synthesis of Competitive Insights
Creation of Competitive Analysis Report
Consumer Insight Gathering
Determining Target Audience
Formulating Research Questions
Selection of Data Gathering Tools
Development of Surveys or Questionnaires
Organizing Focus Group Discussions
Conducting Individual Interviews
Implementing Online Polls
Analysing Customer Reviews
Gathering and Organizing Data
Quantitative and Qualitative Data Analysis
Identification of Consumer Patterns and Trends
Preparation of Consumer Insight Report
Market Trend Examination
Identification of Trend Research Goals
Selection of Relevant Market Segments
Gathering Current Market Data
Historical Market Data Analysis
Identification of Emerging Market Patterns
Analysing Industry News and Reports
Monitoring Social Media and Digital Trends
Conducting Expert Interviews
Interpretation of Market Growth and Decline Trends
Forecasting Future Market Conditions
Impact Assessment of Identified Trends
Finalization of Market Trend Report
Product Comparison
Defining Comparison Criteria
Selection of Comparable Products
Gathering Detailed Product Specifications
Comparing Product Features
Analysing Product Quality and Reliability
Comparing Pricing Strategies
Reviewing Customer Perceptions and Reviews
Assessing Market Acceptance and Popularity
Evaluating Product Design and Packaging
Studying Product Lifecycles
Summarising Comparison Findings
Finalizing Product Comparison Report
SWOT Analysis
Specification of Analysis Objectives
Identification of Company Strengths
Identification of Company Weaknesses
Analysis of External Opportunities
Identification of External Threats
Collection of Relevant Data and Information
Organising Data into SWOT Categories
Prioritising SWOT Factors
Cross-evaluating SWOT Factors
Drawing Conclusions from SWOT Analysis
Developing Strategies from SWOT Results
Finalizing and Documenting SWOT Analysis Report
Strategy Development
Identification of Strategic Goals
Review of SWOT Analysis Results
Determination of Target Market
Formulation of Unique Value Proposition
Development of Marketing Mix Strategies
Creation of Pricing Strategy
Formulation of Distribution Strategy
Planning of Promotional Strategy
Development of Product Positioning Strategy
Mapping out Strategic Implementation Timeline
Identification of Key Performance Indicators
Finalizing the Comprehensive Strategy Plan
Implementation Planning
Reviewing Strategy Plan
Setting Implementation Goals
Assigning Roles and Responsibilities
Detailing Action Steps
Establishing Timeframes and Deadlines
Allocating Resources
Planning for Potential Challenges
Setting Up Monitoring and Evaluation Mechanisms
Documenting the Implementation Plan
Gaining Approval for Implementation
Communication of the Plan to Relevant Teams
Kick-off of Implementation Process
Assessment Review & Refinement
Establishing Review Objectives
Gathering Relevant Project Data
Conducting Performance Analysis
Evaluating Implementation Success
Identifying Areas of Improvement
Analysing Feedback and Critiques
Determining Necessary Refinements
Prioritizing Refinement Actions
Developing Action Plan for Refinements
Implementing Refinement Actions
Monitoring and Evaluating Refinement Success
Documenting Final Assessment and Refinement Report