## Corporate Branding Website Des
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=corporate-branding-website-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Kickoff
Project Briefing
Setting Goals and Objectives
Establishing Project Scope
Identifying Key Stakeholders
Assembling Project Team
Defining Roles and Responsibilities
Developing Initial Project Plan
Setting Up Communication Plan
Arranging Kickoff Meeting
Conducting Kickoff Meeting
Distributing Project Plan
Confirming Project Timescales and Deadlines
Market Research
Identifying Research Objectives
Defining Target Audience
Planning Research Methodology
Designing Questionnaires or Surveys
Collecting Primary Data
Collecting Secondary Data
Analyzing Competitors
Conducting SWOT Analysis
Analyzing Collected Data
Interpreting Research Findings
Developing Consumer Profile
Creating Research Report
Branding Strategy Development
Setting Brand Objectives
Identifying Unique Selling Proposition
Understanding Market Position
Defining Brand Personality
Creating Brand Mission Statement
Developing Brand Values
Designing Brand Logo
Choosing Brand Color Scheme
Crafting Brand Voice
Formulating Brand Messaging
Determining Brand Touchpoints
Creating Brand Guidelines
Website Wireframe Design
Determining Website Goals
Identifying User Paths
Sketching Initial Wireframe
Refining Wireframe Sketch
Creating Digital Wireframe
Designing Navigation Structure
Placing Content Blocks
Incorporating Brand Elements
Reviewing and Revising Design
Finalizing Wireframe Layout
Testing Wireframe Usability
Obtaining Client Approval
Content Creation
Identifying Content Needs
Developing Content Strategy
Researching Topic Areas
Outlining Content Structure
Writing Initial Drafts
Incorporating SEO Keywords
Creating Visual Content
Reviewing and Editing Text
Proofreading for Errors
Finalizing Content Copy
Approving Final Content
Preparing Content for Publishing
Graphic Design
Defining Design Goals
Gathering Design Inspiration
Sketching Initial Concepts
Selecting Color Palettes
Choosing Typography
Creating Illustrations
Designing Icons and Buttons
Developing Graphics for Web Pages
Designing Page Layouts
Reviewing and Revising Designs
Finalizing Graphic Elements
Preparing Designs for Web Integration
Website Development
Selecting Development Tools
Setting up Development Environment
Coding Website Structure
Integrating Graphics and Multimedia
Embedding Content
Configuring Site Navigation
Implementing Responsive Design
Adding Interactive Elements
Testing Site Functionality
Debugging and Troubleshooting
Optimizing for SEO
Preparing for Site Launch
User Testing
Preparing Test Plan
Selecting Test Participants
Designing Test Scenarios
Setting Up Testing Environment
Conducting Initial User Tests
Recording Test Results
Analyzing Test Data
Identifying Usability Issues
Implementing Changes Based on Feedback
Conducting Follow-up Tests
Finalizing Site Modifications
Completing User Testing Report
Website Launch
Finalizing Launch Plan
Conducting Pre-launch Check
Confirming Website Functionality
Setting Up Hosting Environment
Transferring Website Files
Implementing SEO Settings
Testing Site Load Time
Conducting Final User Test
Announcing Launch Date
Going Live
Monitoring Site Performance
Announcing Site Launch
Post-Launch Support and Maintenance
Setting Support Parameters
Assigning Support Team
Monitoring Site Performance
Tracking User Feedback
Handling User Queries
Conducting Regular Site Checks
Implementing Necessary Updates
Backing Up Website Data
Fixing Bugs and Glitches
Optimizing Site Speed
Updating Content Regularly
Reviewing and Renewing Website Security.