## Corporate Promotional Vide
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=corporate-promotional-video
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Briefing
Initial Communication
Stakeholder Identification
Client Consultation
Project Expectation Clarification
Scope Definition
Objective Setting
Budget Discussion
Timeline Establishment
Resource Allocation
Risk Assessment
Approval Gathering
Project Kickoff Meeting.
Concept Development
Market Research
Competitor Analysis
Audience Identification
Brainstorming Sessions
Storyboarding
Concept Drafting
Idea Refinement
Visual Style Determination
Concept Testing
Feedback Collection
Concept Revision
Final Concept Approval.
Scriptwriting
Researching Content
Outlining Structure
Defining Characters
Crafting Dialogue
Establishing Scenes
Developing Plot
First Draft Writing
Script Review
Revisions and Editing
Script Table Read
Incorporating Feedback
Final Script Approval.
Pre-production Planning
Location Scouting
Equipment Listing
Casting Calls
Talent Auditions
Crew Assignments
Shot Listing
Schedule Preparation
Budget Finalization
Set Designing
Costume Planning
Technical Run-through
Pre-production Meeting.
Casting and Crew Selection
Job Description Posting
Application Review
Preliminary Auditions
Callbacks
Talent Interviews
Screen Tests
Role Finalization
Crew Member Shortlisting
Skills Assessment
Crew Interviews
Crew Selection
Contract Signing.
Production Filming
Set Prep
Equipment Setup
Crew Briefing
Scene Blocking
Lighting Arrangement
Camera Positioning
Rehearsals
Makeup and Wardrobe
Sound Checks
Principal Photography
Scene Wrap-up
Daily Footage Review.
Post-production Editing
Footage Backup
Video Logging
Video Assembly
Rough Cut Creation
Fine-Tuning Edits
Transition Application
Color Grading
Special Effects Addition
Title and Credit Insertion
Editing Review
Feedback Incorporation
Final Cut Approval.
Sound and Music Integration
Sound Footage Review
Dialogue Editing
Sound Effects Selection
Sound Effects Integration
Background Music Selection
Music Licensing
Music Integration
Audio Mixing
Foley Editing
Audio Review
Sound Adjustments
Final Audio Approval.
Review and Revision
Initial Viewing
Quality Assurance Check
Feedback Compilation
Key Stakeholder Review
Suggested Changes Listing
Editing for Revisions
Technical Corrections
Revised Version Viewing
Additional Feedback Collection
Final Revisions
Approval Process
Sign Off.
Final Distribution.
Distribution Strategy Planning
Format Conversion
Quality Checking
Media Packaging
Distribution Channel Selection
Release Date Scheduling
Distributor Communication
Content Delivery
Release Monitoring
Audience Engagement
Metrics Analysis
Success Evaluation.