## Corporate websit
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=corporate-website
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Outline
Objective Definition
Stakeholder Identification
Resource Allocation
Team Formation
Budget Estimation
Risk Assessment
Project Schedule Creation
Communication Plan Development
Technology Selection
Project Charter Development
Project Kick-off Meeting
Requirement Gathering
Identifying Information Sources
Stakeholder Interview Planning
Conducting Stakeholder Interviews
Document Analysis
Requirement Elicitation Workshops
Survey Distribution
Survey Analysis
Prototyping
Requirement Prioritization
Requirement Documentation
Requirement Review with Stakeholders
Requirement Approval and Baseline.
Design and Layout Planning
Sketching Site Structure
Developing Wireframes
Creating Mockups
User Interface Design
User Experience Planning
Color Scheme Selection
Typography Selection
Navigation Structure Design
Responsive Design Planning
Graphic Element Creation
Review and Feedback
Design Approval.
Content Development
Content Audit
Keyword Research
Content Strategy Development
Content Calendar Creation
Topic Brainstorming
Content Writing
Graphic Content Creation
Video Content Creation
Content Review
SEO Optimization
Content Approval
Content Scheduling.
Coding and Programming
Technology Stack Definition
Front-End Coding
Back-End Coding
Database Setup
API Integration
Responsive Coding
Functionality Implementation
Error Handling Setup
Security Measures Implementation
Code Review
Bug Fixing
Code Optimization.
Website Testing
Test Plan Creation
Functionality Testing
Usability Testing
Interface Testing
Compatibility Testing
Performance Testing
Security Testing
Responsiveness Testing
Cross-Browser Testing
Test Result Documentation
Bug Reporting
Retesting After Fixes.
Feedback Incorporation
Feedback Collection
Feedback Categorization
Feedback Analysis
Prioritization of Changes
Plan for Incorporation
Coding Changes
Testing Changes
Reviewing Changes
Stakeholder Approval
Documentation Update
User Notification
Feedback Loop Closure.
Deployment
Deployment Planning
Server Configuration
Database Migration
File Transfer
Application Installation
Website Activation
Link Checking
Functionality Verification
Performance Monitoring
Backup Setup
User Access Setup
Deployment Confirmation.
Post-Launch Support
User Support Setup
User Training Sessions
FAQ Creation
Helpdesk Establishment
Dealing with User Queries
Technical Problem Solving
Bug Tracking
Quick Fixes Implementation
User Feedback Collection
Performance Monitoring
Reporting & Documentation
User Satisfaction Assessment.
Maintenance and Updates
Maintenance Schedule Creation
Regular Site Backup
Security Monitoring
Updating Site Content
Software Updates
Functionality Enhancement
User Experience Improvement
SEO Updates
Analytics Review
Troubleshooting and Fixes
System Optimizations
Periodic Reporting.