## e-commerce-developmen
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=e-commerce-development
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Market Research
Identify Target Audience
Understand Customer Needs
Monitor Competitors' Activity
Analyze Market Trends
Study Online Consumer Behavior
Evaluate Product/Service Demand
Review Potential Legal Considerations
Explore Industry Best Practices
Assess Social Media Influence
Examine Seasonal Sales Patterns
Determine Pricing Strategies
Finalize Research Report
Business Plan Drafting
Executive Summary Creation
Company Description Formulation
Market Analysis Compilation
Organization Structure Design
Service or Product Line Definition
Marketing Strategy Development
Sales Strategy Formulation
Funding Request Preparation
Financial Projections Calculation
SWOT Analysis Conducting
Business Plan Review
Business Plan Finalization
E-commerce Platform Selection
Identify Platform Requirements
Research Available Platforms
Assess Platform Scalability
Evaluate Platform Security Features
Compare Pricing Models
Review Customer Support Options
Check Integration Possibilities
Test Platform Usability
Solicit Team Feedback
Make Preliminary Selection
Conduct Platform Trial
Finalize Platform Selection
Website Designing
Define Design Objectives
Create Site Map
Sketch Wireframes
Select Design Template
Choose Color Scheme
Select Fonts and Typography
Create Graphics and Icons
Design Navigation Menu
Develop User Interface
Incorporate Brand Elements
Review and Revise Design
Finalize Website Design
Content Creation
Identify Content Needs
Develop Content Strategy
Research Keywords
Outline Site Pages
Write Product Descriptions
Compose Blog Posts
Create Social Media Content
Design Visual Elements
Proofread and Edit Text
Optimize SEO Content
Review and Revise Content
Finalize and Approve Content
Website Development
Define Technical Specifications
Set Up Development Environment
Create Database Structure
Write Code for Functionalities
Integrate Design Elements
Develop User Registration Features
Configure Payment Gateway
Implement SEO Best Practices
Add Security Features
Test on Different Browsers
Debug and Refine Code
Finalize Website Development
Testing and Quality Assurance
Develop Test Plan
Conduct Functionality Testing
Perform Usability Testing
Carry out Compatibility Testing
Execute Performance Testing
Undertake Security Testing
Review SEO Implementation
Validate Payment Gateway Function
Test on Multiple Devices
Gather User Feedback
Debug and Resolve Issues
Finalize Quality Assurance Review
Website Launch
Set Launch Date
Configure Hosting and Domain
Perform Final Site Check
Backup Website Data
Confirm SEO & Security Features
Schedule Website Downtime
Execute Site Migration
Activate Website Live
Conduct Post-Launch Testing
Announce Website Launch
Monitor Site Performance
Handle User Queries and Feedback
Marketing and Promotion
Define Marketing Goals
Identify Target Audience
Develop Marketing Strategy
Create Promotional Content
Set Up Social Media Campaigns
Implement SEO Strategies
Launch Email Marketing Campaigns
Run Paid Advertisements
Monitor Campaign Performance
Analyze Marketing Data
Adjust Marketing Strategies
Evaluate Overall Marketing Success
Maintenance and Support
Develop Maintenance Plan
Conduct Regular Website Check-ups
Update Website Content
Backup Website Data Regularly
Monitor Website Performance
Apply Security Updates
Resolve Technical Issues
Handle User Queries and Requests
Update SEO Strategies
Keep Up with Industry Trends
Review and Improve User Experience
Evaluate and Update Maintenance Plan