## electric-grid-expansio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=electric-grid-expansion
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Feasibility Analysis
Project Briefing
Data Gathering
Site Inspection
Market Research
Environmental Impact Assessment
Regulatory Compliance Check
Power Demand Analysis
Grid Integration Study
Resource Availability Assessment
Cost-Benefit Analysis
Risk Assessment
Feasibility Report Preparation
Project Specification
Stakeholder Identification
Project Scope Definition
Requirement Gathering
Technical Specification Development
Performance Criteria Establishment
Project Timeline Determination
Budget Estimation
Quality Standards Setting
Resource Allocation Planning
Safety Measures Planning
Contract Terms Drafting
Project Specification Document Preparation
Budget Planning
Financial Goal Setting
Cost Estimation
Revenue Forecasting
Funding Source Identification
Contingency Fund Allocation
Budget Breakdown Preparation
Cash Flow Analysis
Financial Risk Assessment
Budget Approval Seeking
Budget Documentation
Budget Communication
Budget Monitoring Plan Development
Design & Engineering
Initial Concept Development
Structural Designing
Electrical System Designing
Safety Measures Incorporation
Material Selection
Engineering Drawings Creation
Design Verification
Prototype Development
Prototype Testing
Design Adjustments
Final Design Approval
Engineering Documentation Preparation
Procurement
Procurement Planning
Supplier Identification
Request for Proposal Creation
Bid Management
Supplier Evaluation
Contract Negotiation
Purchase Order Issuance
Procurement Scheduling
Goods Receipt Verification
Quality Inspection
Inventory Management
Supplier Payment Processing
Grid Infrastructure Development
Site Preparation
Foundation Setting
Structural Assembly
Electrical Installation
Grid Integration
Safety Measures Implementation
Grid Stabilization
System Optimization
Infrastructure Inspection
Quality Control Check
Preliminary Power Testing
Infrastructure Finalization
Grid Installation
Installation Planning
Power Equipment Procurement
Installation Team Briefing
Safety Measures Enforcement
Equipment Installation
Grid Connection
System Configuration
Initial Power Run
Installation Inspection
Fault Detection & Rectification
Installation Verification
Installation Documentation Preparation
System Testing
Test Planning
Test Case Development
Pre-testing System Check
Functional Testing
Integration Testing
Load Testing
Safety Testing
Fault Identification
Issue Rectification
Retesting
Test Result Documentation
Test Review & Approval
Grid Commissioning
Commissioning Planning
Team & Stakeholder Briefing
Pre-Commissioning Checks
Safety Measures Confirmation
Operational Test Running
Parameter Adjustment
Performance Verification
Final Inspection
Grid Connection Validation
Client Handover
Commissioning Report Preparation
Official Commissioning Ceremony
Maintenance & Monitoring
Maintenance Planning
System Monitoring Setup
Performance Tracking
Preventive Maintenance
Fault Detection
Problem Analysis
Corrective Maintenance
System Re-Testing
Maintenance Documentation
System Optimization
Performance Reporting
Regular Review & Adjustment