## Enterprise Softwar
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=enterprise-software
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Requirement Analysis
Identify Stakeholders
Conduct Stakeholder Meetings
Define Business Goals
Analyze Current Systems
Identify System Requirements
Document Functional Requirements
Document Non-Functional Requirements
Prioritize Requirements
Validate Requirements with Stakeholders
Create System Specifications Document
Review and Approval of Requirements
Prepare Requirement Traceability Matrix
Project Planning
Define Project Scope
Identify Project Deliverables
Determine Necessary Resources
Develop Project Timeline
Establish Project Budget
Define Project Team Roles
Identify Potential Risks
Create Risk Management Plan
Develop Communication Strategy
Finalize Project Plan
Review and Approve Project Plan
Distribute Project Plan to Team
System Design
Define High-Level Design
Identify System Components
Develop Data Model
Outline Interface Design
Create Architectural Blueprint
Specify Hardware and Software needs
Establish System Security Measures
Develop Prototype
Validate System Design with Stakeholders
Modify Design Based on Feedback
Document Detailed System Design
Review and Approve System Design
Software Development
Establish Development Environment
Define Coding Standards
Software Coding
Unit Testing
Debugging and Error Corrections
Integration of Components
Develop User Interface
Develop Database and Functional Operations
Implement Security Features
Optimize Performance
Conduct Code Reviews
Finalize Software Build
Testing Phase
Define Test Plan
Prepare Test Environment
Create Test Cases
Conduct Unit Testing
Perform Integration Testing
Execute Functional Testing
Perform Usability Testing
Conduct Performance Testing
Implement Security Testing
Carry out Regression Testing
Analyze Test Results
Document and Communicate Issues
Deployment/Installation
Confirm Deployment Strategy
Prepare Deployment Documentation
Backup Current System
Set Up Hosting Environment
Install Software on Servers
Verify Installation Success
Migrate Data to New System
Conduct Post-Installation Review
Correct Any Installation Issues
Validate System Functionality
Go-Live Confirmation
Archive Deployment Records
Integration Stage
Identify Integration Points
Develop Integration Plan
Prepare Test Data for Integration
Execute Component Integration
Conduct Integration Testing
Verify Data Consistency
Resolve Integration Issues
Validate System Workflows
Conduct User Acceptance Testing
Confirm Integration Success
Document Integration Steps
Sign-off Integration Completion
System Validation
Define Validation Criteria
Prepare Validation Plan
Conduct Initial System Review
Verify System Functionality
Validate Data Accuracy
Check Compliance with Standards
Conduct User Validation Testing
Confirm System Performance
Validate System Security
Gather User Feedback
Correct Any Validation Issues
Document Validation Results
User Training
Identify Training Needs
Develop Training Plan
Prepare Training Materials
Set Up Training Environment
Conduct Training Sessions
Provide Hands-on Exercises
Answer User Queries
Conduct Training Assessment
Gather Feedback on Training
Address Training Shortcomings
Repeat Training if Necessary
Document Training Completion
Maintenance & Updates
Develop Maintenance Plan
Monitor System Performance
Handle User Support Requests
Troubleshoot Reported Issues
Perform Regular Backups
Update Software Components
Conduct Security Checks
Implement System Enhancements
Validate System after Updates
Provide Periodic Training for Updates
Prepare Maintenance Reports
Review and Update Maintenance Plan