## Exhibitio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=exhibition
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Conceptualization
Idea Generation
Research
Project Scoping
Objective Setting
Theme Selection
Content Development
Format Decision
Audience Identification
Feasibility Analysis
Stakeholder Consultation
Approval Seeking
Timeline Creation
Planning
Site Selection
Space Allocation
Event Schedule Drafting
Resource Identification
Service Provider Recruitment
Staffing Plan Formation
Risk Assessment
Backup Plan Development
Project Plan Finalization
Health and Safety Considerations
Legalities and Permissions
Milestone Setting
Budgeting
Cost Estimation
Funding Identification
Revenue Forecasting
Expense Allocation
Budget Drafting
Financial Risk Assessment
Contingency Fund Planning
Budget Review
Budget Revision
Budget Finalization
Financial Tracking System Setup
Budget Approval Process
Designing
Design Brief Creation
Layout Sketching
Material Selection
Color Scheme Decision
Lighting Plan Development
Branding Integration
Interactive Element Design
Signage and Wayfinding Planning
Design Prototype Development
Design Review and Revision
Design Finalization
Design Approval Process
Sourcing
Resource Inventory
Supplier Research
Quote Requests
Bid Evaluation
Contract Negotiation
Purchase Order Issuing
Delivery Scheduling
Quality Inspection
Inventory Management
Supplier Payment
Documentation and Receipts
Backup Supplier Identification
Marketing
Marketing Plan Development
Target Audience Research
Brand Message Creation
Marketing Material Design
Social Media Strategy Creation
Press Release Writing
Event Listing Submission
Email Campaign Planning
Marketing Collateral Distribution
Paid Advertising Setup
Outreach to Influencers
Marketing Evaluation and Adjustment
Installation
Site Preparation
Equipment Delivery
Exhibit Assembly
Lighting Setup
Signage Installation
Artwork Placement
Interactive Element Installation
Sound System Setup
Safety Inspection
Final Walkthrough
Minor Adjustments
Cleaning and Preparation for Opening
Launching
Final Check
Staff Briefing
VIP Preview
Media Walkthrough
Opening Ceremony
Guest Arrival Management
Guided Tours
Live Event Management
Social Media Coverage
Feedback Collection
Evening Wrap-up
Post-Launch Review
Operation
Daily Opening
Staff Rotation Management
Exhibit Maintenance
Customer Service
Security Monitoring
Feedback Evaluation
Social Media Updates
Ongoing Marketing
Financial Tracking
Visitor Experience Improvement
Event Hosting
Daily Closing
Deconstruction
Deconstruction Planning
Artwork and Exhibit Removal
Equipment Dismantling
Waste Management
Inventory Check
Return of Borrowed Items
Site Cleaning
Repair and Restoration
Final Inspection
Security Clearance
Feedback and Evaluation
Project Closure Report