## Film Festiva
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=film-festival
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Conceptualization
Idea Generation
Industry Research
Target Audience Identification
Festival Objective Setting
Concept Development
Theme Selection
Scope Definition
Feasibility Study
Event Format Selection
Preliminary Timeline Creation
Concept Presentation
Stakeholder Approval
Planning
Goal Setting
Project Team Formation
Task Delegation
Resource Allocation
Detailed Timeline Development
Contingency Planning
Legal Compliance Check
Plan for Special Guests
Food and Beverage Planning
Accommodation Planning
Ticketing Strategy Development
Plan Finalization
Budgeting
Cost Estimation
Revenue Forecasting
Allocation for Venue
Allocation for Marketing
Allocation for Logistics
Allocation for Film Rights
Allocation for Staff and Volunteers
Contingency Fund Setting
Budget Review
Budget Approval
Budget Distribution
Financial Tracking System Setup
Sponsorship and Partnership Acquisition
Sponsor Identification
Partnership Opportunity Research
Sponsorship Package Creation
Partnership Proposal Development
Outreach to Potential Sponsors
Outreach to Potential Partners
Sponsorship Negotiations
Partnership Negotiations
Agreement Drafting
Contract Review
Contract Signing
Public Announcement of Partnerships and Sponsorships
Film Selection
Film Submission Announcement
Film Submission Guidelines Creation
Film Submission Reception
Initial Screening of Films
Detailed Review of Selected Films
Film Rating
Film Selection Committee Meeting
Final Film Selection
Film Rights Acquisition
Film Scheduling
Filmmakers Notification
Public Announcement of Selected Films
Venue and Logistic Arrangements
Venue Search
Venue Evaluation
Venue Booking
Layout and Seating Plan Design
Equipment Checklist Creation
Equipment Rental or Purchase
Catering Arrangements
Transportation Arrangements
Security Planning
Setup and Breakdown Plan Development
Rehearsal Coordination
Venue and Logistics Finalization
Marketing and Promotion
Marketing Strategy Development
Target Audience Segmentation
Branding Material Creation
Press Release Writing
Social Media Campaign Planning
Website Update
Email Marketing Campaign Setup
Print Advertising Design and Distribution
Media Outreach
Influencer or Celebrity Engagement
Ticket Sales Promotion
Marketing Analytics Monitoring
Event Execution
Final Briefing
Venue Setup
Staff and Volunteer Coordination
Guest Registration
Film Screening Management
Q&A Session Organization
Audience Interaction Management
Catering and Refreshment Provision
Security Management
Problem-Solving and Contingency Execution
Event Breakdown
Clean-up and Venue Restoration
Audience Engagement
Social Media Interaction
Audience Polling and Surveys
Live Q&A Sessions
Meet and Greet Opportunities
Audience Feedback Collection
Film Discussion Hosting
Festival Merchandise Distribution
Audience Competition Hosting
Email Communications
VIP Guest Engagement
Audience Recognition Events
Thank You Notes and Follow-ups
Evaluation and Feedback
Survey Creation
Feedback Collection from Audience
Feedback Collection from Staff
Feedback Collection from Sponsors
Social Media Monitoring
Press Coverage Analysis
Financial Review
Goal Achievement Assessment
Strengths and Successes Identification
Areas of Improvement Identification
Lessons Learned Documentation
Post-Event Report Creation