## Food and Drink Festiva
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=food-drink-festival
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Idea Generation
Brainstorming Session
Theme Decision
Research on Similar Events
Food Type Selection
Drink Type Selection
Entertainment Choices
Defining Target Audience
Pricing Strategy
Date and Time Decision
Sustainable Practice Inclusion
Drafting Preliminary Schedule
Initial Risk Assessment
Project Planning
Project Scope Definition
Objective Setting
Task Breakdown
Timeline Establishment
Resource Allocation
Team Formation
Task Assignments
Communication Plan Development
Contingency Plan Creation
Health and Safety Considerations
Project Plan Finalization
Stakeholder Approval
Budget Preparation
Expense Forecasting
Venue Cost Estimation
Vendor Cost Calculation
Marketing Budget Allocation
Entertainment Expense Planning
Staffing Cost Assessment
Equipment Rental Pricing
Insurance Cost Estimation
Miscellaneous Expense Buffering
Income Projection
Budget Balancing
Budget Approval
Venue Selection
Venue Location Criteria Definition
Potential Venue Research
Initial Venue Shortlisting
Site Visits
Space Assessment
Facility and Amenity Check
Accessibility Evaluation
Parking Availability Review
Cost and Contract Negotiation
Venue Availability Confirmation
Final Venue Selection
Venue Booking Confirmation
Vendor Acquisition
Vendor Need Identification
Potential Vendor Research
Initial Vendor Shortlisting
Vendor Interviewing
Product or Service Quality Check
Price Negotiations
Contract Terms Discussion
Payment Terms Agreement
Vendor Selection Decision
Contract Signing
Vendor Onboarding
Vendor Confirmation Communication
Marketing and Promotion
Marketing Strategy Development
Target Audience Identification
Branding and Messaging
Marketing Material Creation
Website and Social Media Updates
Email Marketing Campaign
Social Media Advertising
Press Release Distribution
Partnership and Sponsorship Outreach
Offline Promotion (Posters, Flyers)
Ticket Sales Launch
Ongoing Promotion Monitoring
Ticket Sales
Ticket Pricing Strategy
Ticket Platform Selection
Ticket Types and Categories Establishment
Early Bird Promotion
Ticket Sale Announcement
Online Ticket Sales Management
Physical Ticket Distribution
Sales Tracking and Reporting
Customer Service for Ticket Buyers
Last Minute Sales Push
Ticket Sale Closure
Final Sales Evaluation
Event Execution
Team Briefing
Venue Setup and Decoration
Vendor Setup Supervision
Security and Safety Checks
Event Opening
Guest Reception and Guidance
Program Flow Management
Staff and Vendor Coordination
Unexpected Issue Handling
Clean-Up Management
Event Closing
Post-Event Debrief
Post-Event Analysis
Data Collection
Sales Performance Review
Attendee Count Verification
Feedback and Review Analysis
Vendor Performance Evaluation
Team Performance Assessment
Social Media Engagement Review
Press Coverage Analysis
Budget Versus Actual Cost Review
Success Measurement Against Objectives
Lessons Learned Documentation
Post-Event Report Compilation
Feedback Collection
Feedback Form Development
Online Feedback Platform Setup
Feedback Collection Announcement
Direct Feedback Request to Attendees
Social Media Feedback Solicitation
Vendor and Staff Feedback Request
Feedback Form Distribution at Event
Reminder for Feedback Submission
Collecting and Consolidating Responses
Feedback Analysis and Interpretation
Action Plan Based on Feedback
Thank You Message to Participants