## golf-course-layou
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=golf-course-layout
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Site Analysis
Site Visit
Topographical Mapping
Soil Testing
Hydrological Analysis
Vegetation Survey
Climate Study
Environmental Impact Assessment
Accessibility Analysis
Infrastructure Assessment
Stakeholder Consultation
Project Strengths and Weaknesses Assessment
Site Analysis Report Preparation
Conceptual Design
Project Briefing
Initial Sketching
Review of Site Analysis
Creation of Design Concept
Layout of Holes
Design of Greens
Design of Fairways
Design of Hazards
Preliminary Materials Selection
Presentation of Initial Concept
Revisions Based on Feedback
Final Conceptual Design Preparation
Preliminary Layout
Preliminary Layout Briefing
Basic Course Layout Design
Hole Positioning
Tee and Green Placement
Fairway Mapping
Hazard Distribution
Walking Path Planning
Service and Maintenance Route Planning
Preliminary Infrastructure Planning
Layout Review and Feedback
Layout Revisions
Final Preliminary Layout Approval
Detailed Design
Detailed Design Briefing
Final Course Layout
Final Tee and Green Designs
Detailed Fairway Design
Hazard Detailing
Infrastructure Design
Landscaping and Planting Plans
Irrigation System Design
Materials and Equipment Specifications
Detailed Design Review and Feedback
Design Revisions
Approval of Final Detailed Design
Permit Acquisition
Permitting Requirements Research
Documentation Preparation
Application for Building Permit
Submission of Environmental Impact Report
Application for Water Usage Permit
Application for Construction Noise Permit
Public Notice and Comment Period
Response to Public Comments
Permit Review Meetings
Permit Revision Submission
Final Permit Approval
Permit Documentation Archiving
Construction Planning
Construction Planning Meeting
Final Budget Approval
Scheduling and Timeline Development
Equipment and Material Procurement
Contractor Selection
Site Safety Planning
Waste Management Planning
Project Communication Setup
Quality Control Measures
Contingency Planning
Construction Plan Approval
Construction Plan Documentation
Land Preparation
Site Clearance
Debris Removal
Topsoil Preservation
Land Grading
Drainage Installation
Irrigation System Installation
Soil Conditioning
Grass Seeding Preparation
Tree Removal or Planting
Hazard Area Preparation
Land Preparation Inspection
Land Preparation Documentation
Course Construction
Construction Kick-off Meeting
Base Layer Construction
Green Construction
Fairway Construction
Hazard Construction
Tee Box Construction
Pathway Construction
Installation of Signage
Seeding and Turfing
Construction Inspections
Issue Resolution
Construction Documentation and Completion Report
Landscaping Installation
Landscape Design Review
Soil Preparation for Planting
Tree Planting
Shrub Planting
Flower Bed Installation
Grass Seeding or Turfing
Water Feature Installation
Installation of Benches and Seating Areas
Installation of Lighting
Irrigation System Testing
Landscape Inspection
Maintenance Plan Establishment
Final Inspection & Opening
Pre-Inspection Meeting
Safety Inspection
Quality Control Inspection
Landscape Inspection
Building Code Compliance Inspection
Course Playability Testing
Correction of Identified Issues
Final Project Walk-through
Final Approval and Sign-off
Preparation for Opening Day
Opening Ceremony Planning
Course Opening Day