## highway-constructio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=highway-construction
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Planning
Identify Project Scope
Goals Definition
Stakeholder Identification
Project Team Formation
Risk Assessment
Budget Formulation
Timeline Development
Resource Allocation
Legal Compliance Review
Communication Plan Development
Project Plan Documentation
Plan Approval Process
Site Analysis
Site Visit
Data Collection
Soil Testing
Topography Survey
Climate Analysis
Existing Utilities Assessment
Environmental Impact Study
Traffic Analysis
Accessibility Evaluation
Sun Path and Wind Analysis
Site Analysis Report Preparation
Site Analysis Report Presentation
Design Development
Conceptual Design Drafting
Design Review and Feedback
Detailed Design Development
Structural Analysis
Material Selection Process
Design Modifications
Technical Specifications Definition
Design Validation
Safety Measures Integration
Design Documentation
Presentation of Final Design
Design Approval Process
Utilities Mapping
Utilities Inventory Collection
Local Authority Consultation
Site Inspection for Utilities
Underground Scanning
Data Analysis and Interpretation
Utilities Identification
Utilities Classification
Geospatial Mapping
Creation of Utilities Layout
Validation of Utilities Map
Utilities Map Documentation
Utilities Map Presentation
Pavement Engineering
Pavement Materials Analysis
Pavement Design Conceptualization
Pavement Load Assessment
Geotechnical Investigation
Pavement Thickness Calculation
Drainage System Planning
Pavement Construction Methodology Development
Pavement Maintenance Schedule Planning
Pavement Design Validation
Pavement Design Documentation
Presentation of Pavement Design
Pavement Design Approval Process
Cost Estimation
Scope and Work Identification
Quantity Takeoff
Material Cost Estimation
Labor Cost Estimation
Equipment Cost Estimation
Overhead Cost Estimation
Contingency Cost Calculation
Total Cost Summary
Cost Validation
Budget Review
Cost Documentation
Cost Approval Process
Procurement
Procurement Planning
Vendor Research
Request for Proposal Preparation
Bids Solicitation
Bid Evaluation
Supplier Selection
Contract Negotiation
Contract Awards
Purchase Order Processing
Material Delivery Arrangements
Invoice Verification
Supplier Payment Processing
Construction Phase
Pre-construction Meeting
Site Preparation
Foundation Construction
Structural Framework Construction
Material Installation
Equipment Installation
Quality Control Checks
Safety Compliance Monitoring
Progress Reporting
Snagging List Creation
Construction Rectification
Construction Completion Report
Utility Installation
Utility Layout Review
Excavation for Utilities
Utility Infrastructure Installation
Utility Connections Setup
Utility System Testing
Safety Measures Implementation
Utility Inspection
Utility System Adjustments
Compliance Confirmation
Utility Documentation
Utility Installation Sign-off
Utility Handover Procedure
Project Completion
Final Inspections
Defect Rectification
Completion Documentation
Final Quality Assurance Checks
Final Cost Review
Stakeholder Notification
Project Handover
Project Debriefing
Team Recognition
Post-Completion Audit
Project Closure Report
Lessons Learned Documentation