## Influencer Partnership Progra
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=influencer-partnership-program
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Kickoff
Project Briefing
Team Assembly
Roles and Responsibilities Allocation
Project Timeline Creation
Budget Setting
Resource Planning
Communication Plan Development
Risk Assessment
Project Blueprint Approval
Kickoff Meeting Scheduling
Kickoff Meeting Execution
Task Delegation
Target Audience Identification
Market Analysis
Define Goals and Objectives
Identify Demographics
Understand Psychographics
Assess Consumer Behavior
Analyze Social Media Trends
Identify Key Pain Points
Pinpoint Interests and Hobbies
Map Customer Journey
Develop Audience Personas
Validate Target Audience
Document Target Audience Profile
Influencer Research
Define Influencer Criteria
Identify Potential Platforms
Start Initial Influencer Search
Check Influencer Authenticity
Analyze Influencer Audience
Review Influencer Content Quality
Evaluate Influencer Engagement Rate
Assess Influencer Relevance
Compare Influencer's Values with Brand's
Preliminary Shortlist Creation
Detailed Influencer Evaluation
Final Influencer Shortlist Creation
Outreach Strategy
Define Outreach Goals
Identify Key Messages
Choose Outreach Platforms
Develop Outreach Timelines
Create Outreach Templates
Personalize Outreach Messages
Plan Follow-Up Strategy
Outline Incentive Structure
Prepare Outreach Materials
Conduct Initial Outreach
Implement Follow-Up Strategy
Evaluate Outreach Success
Influencer Engagement
Define Engagement Goals
Develop Relationship Building Strategy
Craft Influencer Pitch
Send Initial Engagement Request
Negotiate Collaboration Terms
Finalize Agreement Details
Sign Contracts
Provide Campaign Briefing
Share Content Guidelines
Maintain Open Communication
Provide Support and Feedback
Evaluate Engagement Success
Content Development
Define Content Objectives
Develop Content Strategy
Create Content Calendar
Draft Initial Content Ideas
Identify Required Resources
Allocate Tasks to Team Members
Develop First Drafts
Review and Revise Content
Finalize Content Pieces
Schedule Content for Publication
Prepare for Content Launch
Conduct Final Content Check
Campaign Launch
Final Campaign Review
Confirm Launch Date
Coordination with Influencers
Set Up Tracking Systems
Prepare Promotion Channels
Send Launch Communication
Activate Launch Sequence
Monitor Initial Performance
Respond to Audience Feedback
Adjust Strategy if Necessary
Document Launch Process
Celebrate Successful Launch
Monitoring and Evaluation
Define Evaluation Metrics
Set up Monitoring Tools
Begin Continuous Monitoring
Collect Data Regularly
Analyze Engagement Metrics
Review Content Performance
Monitor Influencer Activity
Track Audience Response
Evaluate Against Goals
Prepare Evaluation Report
Discuss Findings with Team
Implement Necessary Changes
Feedback and Adjustment
Seek Feedback from Influencers
Collect Audience Feedback
Analyze Feedback Data
Identify Areas for Improvement
Create Adjustment Plan
Discuss Adjustments with Team
Communicate Changes to Influencers
Implement Adjustment Plan
Monitor Effects of Adjustments
Assess Result of Changes
Fine-Tune Adjustment Plan
Document Feedback and Adjustment Process
Project Wrap-Up
Review Project Goals
Assess Overall Performance
Document Successes and Challenges
Conduct Post-Project Analysis
Compile Final Report
Host Project Debrief Meeting
Thank Influencers for Participation
Communicate Results to Stakeholders
Archive Project Documents
Celebrate Success with Team
Establish Post-Project Follow-up
Close Project Officially