## Intrusion Detection System Imp
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=intrusion-detection-system-implementation
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Kick-off
Team Formation
Stakeholder Identification
Scope Definition
Objective Setting
Resource Planning
Budget Estimation
Risk Assessment
Timeline Creation
Project Charter Preparation
Approval Seeking
Project Plan Finalization
Requirements Gathering
Identify Stakeholders
Conduct Interviews
Distribute Questionnaires
Facilitate Workshops
Analyze Existing System
Document Functional Requirements
Document Non-Functional Requirements
Create Use Cases
Validation of Requirements
Prioritize Requirements
Baseline Requirement Document
Obtain Approval on Requirements
System Design
System Architecture Planning
Functional Design Creation
Non-Functional Design Creation
User Interface Designing
Database Structure Design
System Layout Preparation
Technology Selection
Design Review & Analysis
Design Documentation
Internal Approval Process
Stakeholder Approval Process
Design Finalization
Hardware & Software Acquisition
Hardware Requirement Identification
Software Requirement Identification
Vendor Analysis
Request for Proposal (RFP) Preparation
RFP Distribution
Proposal Evaluation
Vendor Selection
Contract Negotiation
Purchase Order Creation
Hardware Delivery & Inspection
Software Procurement & Verification
Documentation & Inventory of Acquisitions
System Configuration
Configuration Planning
Hardware Setup
Software Installation
System Parameter Setting
User Account Creation
Network Configuration
Security Settings Configuration
Backup and Recovery Procedure Setup
Performance Tuning
System Testing
Configuration Documentation
Configuration Completion Validation
System Implementation
Implementation Planning
Environment Setup
System Installation
Data Migration
Rolling Out Features
Integration with Existing Systems
Running Parallel Systems
System Monitoring
Troubleshooting & Debugging
User Feedback Collection
System Modification
Implementation Review
Testing & Validation
Test Planning
Test Case Development
Test Environment Setup
Unit Testing
Integration Testing
System Testing
Performance Testing
User Acceptance Testing
Bug Tracking & Fixing
Regression Testing
Validation Check
Test Completion Reporting
User Training
Training Needs Assessment
Training Material Preparation
Trainer Selection
Training Schedule Planning
Training Environment Setup
Conducting Training Sessions
Hands-On Practice
Doubts Clarification
Assessment Test
Feedback Collection
Refresher Training (if needed)
Training Completion Evaluation
System Deployment
Deployment Strategy Planning
Pre-Deployment Testing
Backup Existing System
System Installation
Data Transfer
System Integration
User Notification
Switching Production to New System
Post-Deployment Testing
Troubleshoot Issues
User Support
Deployment Completion Report
Maintenance & Evaluation
Maintenance Planning
Performance Monitoring
Regular System Audit
Bug Reporting
Software Updates Installation
Hardware Servicing
User Support & Troubleshooting
System Improvement Suggestions
System Modifications
Re-evaluation of System Requirements
Regular System Evaluation
Maintenance Reporting