## landscape-exploratio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=landscape-exploration
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Briefing
Team Formation
Budget Allocation
Goal Setting
Timeframe Establishment
Resource Identification
Risk Assessment
Stakeholder Mapping
Communication Plan Creation
Kick-off Meeting
Project Plan Development
Approval and Commencement.
Influencer Identification
Market Research
Defining Target Audience
Influencer Requirement Identification
Influencer Search
Influencer Shortlisting
Influencer Profile Analysis
Audience Verification
Engagement Rate Check
Content Quality Assessment
Brand Alignment Verification
Influencer Scoring
Final Influencer Selection.
Outreach Planning
Campaign Objective Refinement
Influencer Communication Strategy Development
Outreach Channel Selection
Outreach Message Crafting
Timeline Planning
Budget Finalisation for Outreach
Content Calendar Creation
Outreach Team Allocation
Outreach Material Preparation
Legal Considerations Review
Approval of Outreach Plan
Outreach Plan Implementation Preparation.
Influencer Contact
Contact Information Gathering
Initial Contact Drafting
Contact Channel Decision
Contact Timing Strategy
Initial Contact Execution
Follow-up Schedule Creation
Response Tracking
Feedback Incorporation
Query Resolution
Meeting Scheduling
Contract Discussion Initiation
Contact Record Keeping.
Contract Negotiation
Pre-negotiation Research
Negotiation Team Selection
Negotiation Strategy Planning
Initial Terms Proposal
Influencer Response Assessment
Terms Adjustment
Agreement Drafting
Contract Reviewing
Legal Consultation
Final Contract Drafting
Contract Signing
Contract Documentation.
Content Development
Content Brief Creation
Content Format Decision
Content Idea Generation
Content Outline Development
Content Creation Team Assembly
Content Drafting
Visuals/Graphic Designing
Content Review and Editing
Influencer Content Integration
Legal & Compliance Check
Final Content Review
Content Approval & Scheduling.
Campaign Launch
Final Content Check
Launch Date Confirmation
Influencer Briefing
Launch Team Coordination
Platform Preparation
Launch Announcement
Content Release
Engagement Monitoring
Initial Impact Assessment
Audience Response Management
Real-Time Adjustments
Launch Day Report Generation.
Performance Tracking
Key Performance Indicators (KPIs) Monitoring
Engagement Rate Tracking
Conversion Tracking
Influencer Performance Evaluation
Audience Feedback Collection
Social Media Metrics Analysis
SEO Impact Assessment
Cost Performance Analysis
Traffic Source Monitoring
Content Performance Review
Analytic Report Compilation
Performance Review Meeting.
Results Evaluation
Data Collection
Data Organization
Performance Data Analysis
Goal Achievement Assessment
KPIs Results Evaluation
Influencer Performance Review
Audience Feedback Analysis
ROI Calculation
Successes Identification
Challenges Identification
Lessons Learned Documentation
Evaluation Report Creation.
Campaign Wrap-up.
Campaign Debrief Meeting
Final Report Compilation
Results Presentation
Influencer Feedback Collection
Influencer Relationship Management
Campaign Asset Archiving
Success Celebration
Public Campaign Closure Announcement
Budget Closure and Review
Post-Campaign Audience Engagement
Team Performance Review
Planning for Future Campaigns.