## landscape-improvemen
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=landscape-improvement
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Initial Consultation
Appointment Scheduling
Project Briefing
Client Expectations Discussion
Site Visiting
Preliminary Walkthrough
Clients' Needs Analysis
Existing Conditions Review
Project Scope Definition
Questions & Clarifications
Ideas Exchange
Initial Proposal Presentation
Feedback Collection
Site Assessment
Site Arrival
General Site Survey
Soil Sampling
Drainage Evaluation
Sunlight Exposure Analysis
Existing Vegetation Examination
Landscape Feature Assessment
Wildlife Observation
Historical Analysis
Physical Measurement Recording
Site Photographing
Site Assessment Report Compilation
Design Conceptualization
Design Briefing
Brainstorming Sessions
Preliminary Sketching
Landscape Elements Selection
Design Refinement
Color and Material Palette Development
3D Modeling
Lighting Plan Development
Irrigation Plan Development
Review and Adjustments
Final Design Drafting
Presentation Preparation
Budget Formulation
Cost Research
Material Cost Estimation
Labor Cost Calculation
Equipment Rental Budgeting
Landscape Maintenance Cost Projection
Contingency Fund Allocation
Financial Feasibility Analysis
Budget Optimization
Draft Budget Preparation
Budget Review and Adjustment
Final Budget Approval
Budget Communication to Stakeholders
Material Procurement
Material List Preparation
Vendor Identification
Price Quotation Request
Quote Comparison
Vendor Selection
Material Quality Check
Order Placement
Delivery Scheduling
Order Tracking
Material Receipt
Quality Verification on Delivery
Material Storage Arrangement
Site Preparation
Site Clean-up
Old Plant Removal
Soil Preparation
Drainage System Setup
Marking Out areas
Leveling Ground
Root Barrier Installation
Hard Surfaces Clearance
Excavation for Structures
Soil Amendments
Initial Watering
Site Safety Measures Implementation
Landscape Installation
Plant Delivery
Hardscape Construction
Planting Bed Creation
Tree and Shrub Planting
Flower Installation
Grass Seeding or Sod Laying
Irrigation System Installation
Lighting Setup
Mulch Application
Decorative Elements Installation
Initial Care Instructions
Waste Material Disposal
Structural Additions
Structural Plan Review
Material Delivery for Structures
Foundation Preparation
Frame Construction
Wall Installation
Roofing Setup
Door and Window Fitting
Electrical and Plumbing Work
Interior Finishing
Exterior Finishing
Safety Checks
Cleanup and Debris Removal
Final Touches
Area Inspection
Minor Adjustments
Additional Planting
Ornament Placement
Final Mulch Application
Final Watering
Lighting Check
Furniture Arrangement
Surface Cleaning
Safety Barrier Removal
Final Photography
Project Handover Preparation
Project Review & Completion
Final Walk-through
Quality Assurance Check
Defect Identification
Correction of Identified Issues
Client Review Meeting
Feedback Collection
Final Adjustments
Completion Documentation
Final Payment Processing
Handover to Client
Post-Completion Support Discussion
Project Closure