## Living Room Revam
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=living-room-revamp
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Initial Consultation
Appointment Scheduling
Client Meeting Preparation
On-site Visit
Client Brief Collection
Existing Layout Documentation
Room Measurements
Photo Documentation
Client Preferences Identification
Discussion on Budget
Timeline Establishment
Consultation Summary
Agreement Formulation
Scope Definition
Project Objectives Setting
Requirements Gathering
Constraints Identification
Deliverables Definition
Scope Statement Development
Work Breakdown Structure Creation
Project Milestones Determination
Risk Assessment
Resource Allocation Planning
Cost Estimation
Scope Baseline Establishment
Scope Documentation and Approval
Design Development
Conceptual Design Creation
Preliminary Layout Sketching
Material and Color Scheme Selection
Furniture and Fixture Designing
Floor Plan Development
3D Model Visualization
Design Review and Adjustment
Detailed Design Finalization
Client Approval on Design
Technical Drawing Preparation
Execution Plan Development
Design Documentation Completion
Budgeting & Costing
Budget Requirements Identification
Cost Estimation for Materials
Labor Cost Evaluation
Furniture and Fixtures Pricing
Cost Estimation for Services
Contingency Planning Costing
Detailed Budget Preparation
Budget Review and Adjustment
Final Budget Compilation
Client Budget Presentation
Client Budget Approval
Budget Documentation and Filing
Material Procurement
Material List Compilation
Vendor Research
Price Comparison
Vendor Selection
Order Placement
Invoice Verification
Payment Processing
Shipment Tracking
Material Receipt
Quality Inspection
Inventory Management
Procurement Documentation
Furniture Selection
Furniture Needs Identification
Style and Design Consideration
Size and Space Evaluation
Furniture Suppliers Research
Price and Quality Comparison
Furniture Selection
Client Approval for Selection
Order Placement
Payment Processing
Delivery Scheduling
Furniture Assembly
Furniture Inspection and Verification
Painting & Renovations
Space Preparation
Old Paint Removal
Surface Smoothing
Primer Application
Color Mixing
First Coat Painting
Drying Time
Second Coat Painting
Final Paint Touch-ups
Paint Cleanup
Renovation Works
Renovation Cleanup & Verification
Installation & Arrangement
Installation Planning
Unpacking of Furniture
Furniture Assembly
Fixture Installation
Electrical & Plumbing Setup
Furniture Placement
Artwork and Decor Installation
Light Fixtures Setup
Window Treatment Installation
Carpet and Rug Placement
Room Arrangement Finalization
Installation & Arrangement Verification
Final Touch-ups
Comprehensive Review
Paint Touch-ups
Furniture Adjustment
Fixture Check and Correction
Lighting Adjustment
Decor Placement Review
Carpet and Rug Adjustment
Cleaning and Dusting
Overall Look Improvement
Quality Assurance Check
Client Walk-through Preparation
Final Touch-ups Documentation
Project Closure & Review
Project Completion Verification
Client Final Walk-through
Addressing Client's Feedback
Final Adjustments if Necessary
Project Documentation Completion
Financial Settlement
Project Handover
Post Project Evaluation
Lessons Learned Documentation
Team Debriefing
Project Closure Reporting
Client Satisfaction Survey