## Luxury Vill
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=luxury-villa-construction
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Conceptual Design
Client Consultation
Project Brief Development
Site Analysis
Initial Sketching
Preliminary Design Creation
Design Review with Client
Design Alterations
Drafting Conceptual Plans
Creating Conceptual 3D Model
Finalizing Conceptual Design
Client Approval
Preparing Design Presentation
Feasibility Study
Identifying Project Objectives
Gathering Relevant Data
Market Analysis
Site Evaluation
Legal Compliance Check
Environmental Impact Assessment
Cost Estimation
Profitability Analysis
Risk Assessment
Formulating Alternative Solutions
Drafting Feasibility Report
Presenting Feasibility Study to Client
Design Development
Detailed Design Briefing
Advanced Sketching
Material and finish selection
Structural System Planning
Electrical and Plumbing Design
HVAC System Design
Interior Space Planning
Exterior Design Refinement
Detailed 3D Modeling
Client Design Review
Design Adjustments
Final Design Approval
Construction Documentation
Document Planning
Technical Drawing Preparation
Material Specification Documentation
Creating Detailed Floor Plans
Elevations and Section Drawings
Electrical, Plumbing and HVAC Plans
Landscape Design Documentation
Construction Detailing
Preparing Tender Documents
Compliance Check with Building Codes
Final Document Review
Construction Document Submission
Regulatory Approval
Preparation for Submission
Submission of Building Plans
Local Authority Consultation
Environmental Clearance
Fire Safety Approval
Structural Safety Approval
Water and Sewage Approval
Energy Efficiency Compliance
Accessibility Compliance
Responding to Queries
Revisions if Necessary
Obtaining Approval Certificate
Contractor Selection
Drafting Contractor Requirements
Publishing Tender Notice
Pre-Qualification of Contractors
Tender Document Distribution
Receiving Bids
Bid Analysis
Contractor Shortlisting
Conducting Interviews
Reviewing Previous Work
Checking References
Contract Negotiation
Final Contractor Selection
Construction Phase
Site Mobilization
Foundation Construction
Framing and Structural Work
Roofing and Exteriors
Electrical and Plumbing Installation
HVAC System Installation
Interior Finishing
Landscaping and Exterior Works
Quality Control Checks
Health and Safety Inspections
Snagging and Final Touches
Construction Completion and Clean-up
Villa Interior Design
Client Style Consultation
Space Planning
Color Scheme Selection
Furniture Selection
Lighting Design
Selection of Art and Accessories
Fabric and Textile Choices
Custom Cabinetry and Built-Ins Design
Floor and Wall Coverings Selection
Procurement of Interior Elements
Installation of Furnishings and Decor
Final Interior Styling and Client Reveal
Landscaping Design
Site Analysis and Survey
Client Consultation on Landscape Preferences
Creation of Preliminary Design
Selection of Plant Species
Hardscape Planning
Irrigation System Design
Lighting Design for Landscape
Client Review of Landscape Design
Design Revisions if Needed
Finalizing Landscape Design
Preparing Planting and Construction Plans
Submitting Final Landscape Design to Client
Project Closeout
Completion of Final Inspections
Punch List Development
Remediation of Punch List Items
Final Walk-Through with Client
Obtaining Occupancy Permit
Final Clean-up
Handover of Villa to Client
Submission of Final Documentation
Post-Construction Warranty Discussions
Financial Settlement with Contractors
Project Evaluation
Project Closure Report