## marketing-strateg
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=marketing-strategy
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Market Research
Identifying Research Needs
Formulating Research Questions
Designing the Research Study
Defining the Sample Size
Data Collection Method Selection
Data Collection Tool Preparation
Pilot Test of the Tool
Main Data Collection
Data Sorting and Cleaning
Data Analysis
Interpretation of Results
Final Report Writing and Presentation
Competitive Analysis
Identifying Competitors
Defining Parameters for Analysis
Gathering Information about Competitors
Analysing Competitors' Strengths
Analysing Competitors' Weaknesses
Understanding Competitors' Product & Service Offerings
Assessing Competitors' Marketing Strategies
Evaluating Competitors' Pricing Structures
Analysing Competitors' Market Share
Understanding Competitors' Customer Base
Identifying Competitors' Unique Selling Propositions
Summarising and Presenting Findings
Target Audience Identification
Defining the Product or Service
Identifying the Broad Market Scope
Segmenting the Market
Profiling the Market Segments
Evaluating Market Segment Attractiveness
Determining Customer Needs
Identifying Customer Preferences
Understanding Customer Motivations
Assessing Buying Behavior
Selecting Primary Target Segments
Profiling Target Customer Persona
Validating and Documenting the Target Audience Profile
Setting Objectives
Understanding Organizational Goals
Analyzing Marketing Mission
Identifying Key Performance Indicators (KPIs)
Brainstorming Objectives
Aligning Objectives with Market Opportunities
Setting Specific Objectives
Establishing Measurable Objectives
Defining Achievable Objectives
Setting Realistic Objectives
Setting Time-Bound Objectives
Preparing an Objectives Document
Validating and Approving Objectives
Marketing Channels Selection
Understanding Product or Service
Identifying Channel Objectives
Determining Target Audience Preference
Researching Available Channels
Evaluating Channel Reach
Assessing Channel Costs
Comparing Channel Effectiveness
Prioritizing Potential Channels
Selecting Appropriate Channels
Justifying Channel Selection
Finalising Channel Mix
Documenting Channel Strategy
Budget Planning
Defining Financial Goals
Reviewing Historical Marketing Budgets
Identifying Available Resources
Evaluating Marketing Channel Costs
Estimating Campaign Expenses
Allocating Funds for Each Marketing Activity
Factoring in Contingency Costs
Revising and Adjusting Budget Plan
Obtaining Approval for Budget
Setting up Budget Tracking System
Communicating Budget to Relevant Teams
Documenting Final Budget Plan
Strategy Formation
Reviewing Goals and Objectives
Identifying Strategic Options
Aligning Strategies with Target Audience
Matching Strategies with Marketing Channels
Incorporating Competitive Analysis Findings
Establishing Key Messages
Defining Marketing Tactics
Sequencing Marketing Actions
Estimating Expected Results
Reviewing Strategy with Stakeholders
Making Necessary Adjustments
Finalizing and Documenting Marketing Strategy
Content Development
Defining Content Goals
Identifying Target Audience Needs
Creating a Content Calendar
Brainstorming Content Ideas
Selecting Content Formats
Outlining Content Structure
Researching for Content Creation
Writing and Creating Content
Incorporating Brand Messaging
Reviewing and Editing Content
Optimizing Content for SEO
Approving and Scheduling Content
Implementation
Finalizing Implementation Plan
Coordinating with Marketing Teams
Setting up Marketing Channels
Allocating Responsibilities
Training Team Members
Launching Initial Marketing Activities
Monitoring and Adjusting Campaigns
Engaging with Audience
Analyzing Short-term Results
Making Necessary Alterations
Ensuring Consistency Across Channels
Documenting Implementation Process
Monitoring and Evaluation
Setting up Monitoring Tools
Defining Key Performance Indicators (KPIs)
Tracking Metrics Regularly
Gathering Feedback
Conducting Performance Reviews
Analyzing Data and Metrics
Comparing Actual vs. Expected Results
Identifying Areas for Improvement
Making Adjustments to Strategy
Evaluating Overall Success
Reporting Findings to Stakeholders
Documenting Lessons Learned