## Mobile App Interfac
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=mobile-app-interface-creation
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Requirements Gathering
Stakeholder Identification
Scope Definition
Business Analysis
User Research
Functional Requirements Identification
Non-functional Requirements Identification
Prioritizing Requirements
Requirements Documentation
Requirements Validation
Prototyping
User Acceptance Testing
Final Requirements Approval
Project Planning
Project Objective Definition
Preliminary Budgeting
Project Timeline Creation
Identification of Necessary Resources
Team Formation
Task Allocation
Creation of Work Breakdown Structure
Risk Assessment
Planning for Quality Assurance
Communication Plan Development
Project Plan Documentation
Project Plan Approval
User Interface Design
User Persona Development
Information Architecture Design
Wireframe Creation
Mockup Design
Color Scheme Selection
Typography Selection
Icon Design
User Flow Mapping
Interactivity Design
Prototype Creation
Usability Testing
Design Revisions and Finalization
App Development
Technology Stack Selection
Development Environment Setup
Database Design
Backend Development
Frontend Development
API Integration
User Authentication Setup
App Security Measures Implementation
Code Review and Optimization
Version Control Setup
App Compilation
Initial App Deployment
Functionality Testing
Test Plan Creation
Test Case Development
Test Environment Setup
Unit Testing
Integration Testing
System Testing
User Interface Testing
Performance Testing
Security Testing
Compatibility Testing
Regression Testing
Test Report Generation
User Feedback
User Feedback Strategy Development
User Testing Group Selection
User Test Instructions Creation
User Test Deployment
Monitoring User Test Progress
User Experience Survey Development
User Experience Survey Deployment
Collection of User Feedback
Feedback Analysis
Identification of Required Changes
Feedback Reporting
User Feedback Roundup Meeting
Debugging and Improvements
Error Report Collection
Prioritizing Bugs
Debugging Session Planning
Code Walkthrough
Error Replication
Problem Isolation
Bug Fixing
Code Optimization
Feature Improvement
Code Review Post-debugging
Regression Testing Post-debugging
Update Documentation
Beta Testing
Beta Test Planning
Beta Version Preparation
Beta Testers Recruitment
Beta Testing Guidelines Creation
Beta Version Release
User Training for Beta Version
Monitoring Beta Testing
Collecting Beta Feedback
Analyzing Beta Feedback
Bug Tracking and Fixing
Incorporating User Feedback
Beta Test Review and Documentation
App Release
Final Version Approval
Pre-release Testing
App Store Optimization
App Submission Preparation
App Store Submission
App Store Review Process
App Release Planning
Official Release Announcement
User Notification
App Download Monitoring
Customer Review Management
Post-release Review and Analysis
Maintenance and Updates
Performance Monitoring
User Feedback Collection
Bug Tracking
Prioritizing Updates
Update Development
Testing Updates
Scheduling Downtime for Updates
Implementing Updates
Post-update Testing
Update Announcement
User Support and Troubleshooting
Review and Analysis of Update Impact