## Mobile Applicatio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=mobile-application-development
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Concept Development
Idea Generation
Problem Identification
Solution Proposal
Target Audience Definition
Competitor Analysis
Value Proposition Formulation
Feature Listing
Technical Feasibility Assessment
Revenue Model Planning
Platform Selection
App Style Determination
Concept Approval
Market Research
Define Research Objectives
Identify Target Market
Select Research Methodology
Develop Research Questionnaire
Conduct Primary Research
Gather Secondary Data
Analyze Competitors' Apps
Study Market Trends
User Behavior Analysis
Interpret Research Data
Draw Conclusions
Prepare Research Report
Project Planning
Define Project Scope
Identify Project Deliverables
Breakdown of Work Structure
Resource Allocation
Cost Estimation
Time Frame Setting
Create Milestones
Risk Assessment
Communication Plan Making
Set Quality Standards
Develop Contingency Plan
Finalize Project Plan
UX/UI Design
Understand User Needs
Create User Personas
Develop User Flow
Wireframe Designing
Prototype Designing
User Interface Sketching
Select Color Schemes
Choose Typography
Design App Icons
Create Design Guide
Test Design Usability
Finalize UX/UI Design
Prototype Creation
Understand Requirements
Sketch Layout
Define Interaction Details
Create Interactive Prototype
Test Initial Usability
Collect Feedback
Refine Prototype
Conduct Iterative Testing
Fix Usability Issues
Validate Prototype with Stakeholders
Revise According to Feedback
Finalize Prototype
App Development
Setup Development Environment
Implement App Structure
Develop Core Functions
Create User Interface
Integrate APIs
Program Interactions
Develop Secondary Functions
Link Database
Optimize Performance
Code Review
Integrate Design Elements
Finalize App Development
Testing Phase
Create Test Plan
Setup Testing Environment
Conduct Functionality Testing
Perform Usability Testing
Run Compatibility Tests
Implement Security Testing
Execute Performance Testing
Initiate Interface Testing
Carry Out Regression Testing
Investigate & Fix Bugs
Re-run Failed Tests
Prepare Testing Report
Bug Fixing
Identify Bugs
Categorize Bugs
Prioritize Bugs
Assign Bugs to Developers
Debug Code
Validate Fixes
Re-test App Functions
Document Fixes
Update Bug Status
Conduct System Testing
Review Bug Reports
Finalize Bug Fixing
App Launch
Finalize Launch Date
Prepare Press Release
Optimize App Store Listing
Plan Marketing Activities
Confirm App Store Approval
Promote Pre-launch
Launch App on Selected Platforms
Execute Marketing Activities
Monitor App Performance
Gather User Feedback
Promote User Reviews
Analyze Launch Success
Post-Launch Support
Monitor User Feedback
Provide User Support
Address User Complaints
Update App Regularly
Monitor App Performance
Optimize App Based on Analytics
Communicate with Users
Implement New Features
Fix Emerging Bugs
Improve User Experience
Promote App Updates
Maintain App Security