## Mobile Gam
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=mobile-game-development
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Concept Development
Idea Generation
Feasibility Assessment
Theme Selection
Game Genre Determination
Gameplay Mechanics Outline
Storyline Development
Character Sketcing
Art Style Selection
Sound & Music Planning
User Interface Design Concept
Monetization Strategy Development
Concept Document Creation
Market Research
Market Identification
Competitor Analysis
Consumer Behavior Study
Trend Forecasting
Demographics Analysis
Platform Selection Research
Player Motivation Research
Pricing Strategy Research
Overseas Market Analysis
Legal and Compliance Research
Market Growth Prediction
Research Report Compilation
Project Planning
Objectives Definition
Scope Setting
Budgeting
Team Formation
Role Allocation
Timeframe Estimation
Risk Assessment
Resource Planning
Project Management Method Selection
Milestone Setting
Communication Plan Creation
Project Plan Documentation
Game Design
Gameplay Mechanic Finalization
Level Design
User Interface Designing
Character Designing
Artwork Development
Sound and Music Composition
Control Scheme Development
Difficulty Balancing
Reward System Creation
Game Progression Planning
Multiplayer Design (if applicable)
Game Design Document Creation
Prototyping
Core Mechanic Prototyping
Level Prototype Creation
User Interface Prototype Development
Character Prototype Development
Control Scheme Testing
Artwork and Graphic Prototype Creation
Sound and Music Prototype Testing
Gameplay Flow Testing
Difficulty Level Testing
Reward System Testing
Multiplayer Prototype Testing (if applicable)
Prototype Refinement
Coding & Integration
Technology Stack Selection
Game Engine Setup
Coding Game Mechanics
Developing Game Levels
User Interface Implementation
Character Development Coding
Graphics and Art Integration
Sound and Music Integration
Control Scheme Implementation
Reward System Coding
Multiplayer Functionality Coding (if applicable)
Code Review and Optimization
Testing
Test Plan Creation
Unit Testing
Integration Testing
Functionality Testing
User Interface Testing
Gameplay Testing
Performance Testing
Compatibility Testing
Security Testing
Multiplayer Testing (if applicable)
User Acceptance Testing
Bug Reporting and Tracking
Debugging
Bug Prioritization
Reproducing Reported Bugs
Code Review for Debugging
Issue Isolation
Root Cause Analysis
Code Fixing
Unit Testing Post-Fix
Integration Testing Post-Fix
Regression Testing
Performance Testing Post-Fix
User Acceptance Testing Post-Fix
Bug Fix Documentation
Launch & Distribution
Final Build Creation
App Store Submission
Launch Marketing Strategy Development
Press Release Writing
Media Outreach
Social Media Promotion
Launch Event Planning
User Manual and Support Documentation Creation
Launch Day Monitoring
User Feedback Collection
Post-Launch Marketing Activities
Distribution Analytics Monitoring
Post-Launch Support
User Feedback Review
Technical Support Provision
Bug Tracking
Ongoing Game Updates
New Content Creation
Performance Optimization
Community Engagement
Social Media Management
User Retention Strategies
Analytics and Metrics Review
Continued Marketing Efforts
Postmortem Analysis