## modular-home-assembl
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=modular-home-assembly
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Design Approval
Client Briefing
Concept Development
Preliminary Sketching
Client Feedback
Design Refinement
Material Selection
Cost Estimation
Technical Drawings
Building Code Compliance
Final Design Presentation
Client Approval
Documentation Completion
Site Preparation
Site Assessment
Permits Acquisition
Site Clearing
Soil Testing
Land Leveling
Foundation Marking
Drainage Setup
Temporary Facilities Setup
Equipment Mobilization
Material Ordering
Safety Measures Implementation
Site Readiness Confirmation
Module Fabrication
Materials Sourcing
Module Design Review
Equipment Preparation
Component Manufacturing
Framework Assembly
Insulation Installation
Internal Fittings Setup
Exterior Cladding Attachment
Plumbing and Electrical Installation
Quality Control Check
Module Protection
Storage and Inventory Management
Transportation Planning
Module Measurement
Route Identification
Transport Regulation Review
Vehicle Selection
Load Planning
Schedule Setting
Road Permits Application
Safety Protocol Development
Contingency Planning
Cost Analysis
Transport Team Briefing
Final Plan Approval
Module Delivery
Pre-Delivery Inspection
Loading Process
Transport Vehicle Verification
Safety Checks
Delivery Schedule Confirmation
On-Road Monitoring
Traffic Management Coordination
Site Arrival Notification
Unloading Preparation
Module Unloading
Site Placement
Delivery Completion Confirmation
Site Assembly
Site Layout Review
Equipment Positioning
Module Positioning
Foundation Alignment
Module Connection
Structural Inspection
Weatherproofing
System Integration
Fixtures Installation
Finishing Touches
Clean Up
Assembly Completion Verification
Utility Connection
Utility Mapping
Equipment Preparation
Trench Digging
Pipe Installation
Wiring and Cable Laying
Connection to Main Supply
Safety Measures Enforcement
System Testing
Fault Detection and Rectification
Meter Installation
Utility Company Notification
Final Approval and Activation
Interior Finishing
Space Planning
Wall Treatment
Ceiling Finishing
Floor Covering Installation
Door and Window Installation
Electrical Fixtures Setup
Plumbing Fixtures Installation
Cabinetry and Shelving Installation
Painting and Wallpapering
Decorative Details Addition
Furniture Placement
Final Clean-up and Inspection
Exterior Landscaping
Landscape Design Approval
Soil Preparation
Grading and Leveling
Drainage System Installation
Plant Selection
Tree and Shrub Planting
Lawn Establishment
Garden Features Installation
Outdoor Lighting Setup
Pathways and Patio Construction
Irrigation System Setup
Final Landscaping Inspection
Final Inspection
Inspection Schedule Setting
Document Preparation
Pre-Inspection Review
Structural Integrity Check
Interior Inspection
Exterior Inspection
Utility System Testing
Safety and Compliance Review
Defects Identification
Corrective Action Plan
Reinspection
Final Approval and Certification