## office-building-constructio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=office-building-construction
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Initial Conceptualization
Project Briefing
Client Requirements Gathering
Market Research
Feasibility Study
Sustainability Analysis
Brainstorming Sessions
Preliminary Design Sketching
Review and Modifications
Final Concept Approval
Preliminary Cost Estimation
Timeframe Establishment
Phase Completion Assessment.
Site Evaluation and Acquisition
Identification of Potential Sites
Preliminary Site Visits
Site Selection Criteria Development
Detailed Site Analysis
Legal Check for Land Ownership
Soil and Environmental Testing
Accessibility and Infrastructure Assessment
Negotiation with Land Owners
Cost Evaluation of Purchase/Lease
Legal Documentation for Acquisition
Land Purchase/Lease Finalization
Site Securement and Preparations.
Preliminary Design and Planning
Assembling Design Team
Initial Client Consultation
Drafting Preliminary Blueprints
Space Planning
Material Selection
Initial Structural Analysis
Incorporating Sustainability Measures
Compliance Check with Building Codes
Rough Cost Estimation
Preliminary Design Presentation to Client
Client Feedback and Revisions
Final Approval of Preliminary Design.
Detailed Design Development
Detailed Blueprint Creation
In-depth Structural Analysis
Electrical and Plumbing Plan Development
HVAC System Design
Material Specification and Ordering
Safety and Security Planning
Landscape Designing
Detailed Cost Estimation
3D Modeling and Visualization
Revisions Based on Detailed Analysis
Final Design Presentation to Client
Final Design Approval and Documentation.
Budgeting and Financing
Cost Estimation Review
Financial Resources Assessment
Project Budget Preparation
Contingency Fund Allocation
Financing Options Research
Loan Application Preparation (if needed)
Negotiation with Financial Institutions
Securing Financing Approval
Budget Presentation to Client
Budget Approval and Sign-off
Fund Allocation and Management Plan
Financial Risk Assessment and Mitigation.
Permit and Regulation Approval
Research on Local Building Regulations
Preparation of Permit Application Documents
Submission of Building Plans to Authority
Addressing Queries from Regulatory Authorities
Compliance Assurance with Environmental Regulations
Obtaining Fire Safety Approval
Securing Approval for Utility Connections
Application for Construction Permit
Paying Required Regulatory Fees
Receipt of Permit and Regulation Approval
Keeping a Record of all Approvals
Informing All Stakeholders of Approvals.
Construction Phase
Contractor Selection and Hiring
Site Preparation and Groundbreaking
Foundation Laying
Building Frame Construction
Roofing and Wall Installation
Plumbing and Electrical Infrastructure Setup
Window and Door Installation
Interior Construction and Finishing
Exterior Construction and Finishing
Landscaping and Site Clean-up
Construction Review and Quality Checks
Final Construction Inspection and Sign-off.
Interior Setup and Furnishing
Interior Design Conceptualization
Furniture Selection and Ordering
Paint and Wallpaper Selection
Lighting Plan Development
Flooring Installation
Wall Paint and Wallpaper Application
Furniture and Fixture Installation
Lighting Fixtures Installation
Decor Elements Placement
Artwork and Accessories Setup
Final Interior Inspection
Client Approval of Interior Setup.
Inspections and Certifications
Scheduling of Inspections
Building Safety Inspection
Electrical System Inspection
Plumbing System Inspection
HVAC System Inspection
Fire Safety Inspection
Accessibility Inspection
Environmental Compliance Review
Rectification of Identified Issues
Re-inspection (if required)
Issuance of Certificates of Compliance
Keeping Records of all Inspections and Certifications.
Building Handover and Occupancy.
Completion Documentation Preparation
Building Cleaning and Preparations for Handover
Final Walkthrough Planning
Client Final Walkthrough and Inspection
Addressing any Last-minute Fixes
Handover of Completion Documents
Transfer of Property Ownership (if applicable)
Handover of Keys and Access Control
Guidance on Building Maintenance and Operations
Official Handover Ceremony
Occupancy Permits Application (if needed)
Client Move-in and Start of Occupancy.