## Office Workstations Setu
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=office-workstations-setup
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Briefing
Goals Definition
Scope Identification
Team Assembly
Assigning Roles
Budget Estimation
Timeline Development
Resource Allocation
Risk Assessment
Stakeholder Engagement
Project Plan Approval
Kickoff Meeting
Needs Assessment
Employee Survey
Data Collection
Workstation Analysis
Equipment Needs Identification
Software Requirements Gathering
Workspace Layout Planning
Ergonomics Evaluation
Workflow Analysis
Technology Gap Analysis
Cost-Benefit Analysis
Needs Assessment Report
Recommendations and Approval
Workstation Design
Functionality Assessment
Layout Sketching
Equipment Placement
Ergonomic Designing
Technology Integration Plan
Safety Measures Incorporation
Design Review
Mock-Up Creation
Feedback Collection
Design Modification
Final Design Approval
Design Documentation
Procurement
Vendor Research
Request for Proposals
Bid Receiving
Bid Evaluation
Vendor Selection
Contract Negotiation
Purchase Order Issuing
Delivery Scheduling
Equipment Receiving
Quality Inspection
Inventory Documentation
Payment Processing
Workstation Assembly
Assembly Team Formation
Assembly Instructions Review
Workspace Preparation
Equipment Unboxing
Furniture Assembly
Computer Setup
Peripheral Device Connection
Network Cabling
Workspace Cleanup
Functionality Testing
Assembly Errors Rectification
Assembly Completion Verification
Software Installation
Software Requirements Verification
Installation Plan Development
Installer Downloads
Antivirus Installation
Operating System Installation
Driver Updates
Application Installation
Software Configuration
System Updates
Software Testing
Problem Troubleshooting
Installation Report Preparation
Network Configuration
Network Design Review
Configuration Plan Development
Network Equipment Setup
IP Address Assigning
Router Configuration
Wireless Network Setup
Firewall Settings
Network Security Measures
Connectivity Testing
Speed and Performance Testing
Network Troubleshooting
Network Documentation Preparation
Quality Assurance
QA Plan Development
Functionality Inspection
Hardware Quality Control
Software Compatibility Testing
Network Performance Assessment
Ergonomics Review
Safety Measures Evaluation
Feedback Collection
Problem Identification
Issue Resolution
Final QA Check
Quality Assurance Report Preparation
Employee Training
Training Needs Analysis
Training Program Design
Trainer Selection
Training Material Preparation
Training Schedule Planning
Employee Notification
Training Sessions Conducting
Hands-on Training
Troubleshooting Guidance
Feedback Collection
Post-Training Support
Training Effectiveness Evaluation
Project Closure
Project Completion Verification
Final Deliverables Review
Client Approval
Documentation Finalization
Final Budget Review
Project Debriefing
Team Acknowledgment
Lessons Learned Documentation
Project Success Celebration
Project Closure Report
Archiving Project Files
Project Closure Announcement