## Corporate Intrane
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=online-learning-portal-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Briefing
Identifying Stakeholders
Defining Project Scope
Formulating Objectives
Setting Project Timeline
Allocating Resources
Establishing Team Roles
Risk Assessment
Creating Project Charter
Soliciting Stakeholder Approval
Project Kickoff Meeting
Documenting Project Plan
Requirement Gathering
Stakeholder Identification
Requirement Identification Workshop
User Interview Sessions
Survey Design and Distribution
Use-Case Analysis
Documenting Functional Requirements
Documenting Non-Functional Requirements
Requirement Prioritization
Requirement Validation
Creating Requirement Specification Document
Requirement Review with Stakeholders
Finalizing and Freezing Requirements
System Design
Defining System Elements
Logical Designing
Physical Designing
Database Modelling
User Interface Designing
System Architecture Planning
Data Flow Diagram Creation
System Security Design
Creating Technical Specifications
Design Review with Stakeholders
Design Validation
Finalizing System Design Document
Development Phase
Setting Up Development Environment
Coding of Modules
Integration of Components
User Interface Implementation
Database Integration
System Configuration
Version Control Setup
Code Review Sessions
Debugging Code
Software Build Creation
Internal Testing
Preparing for Deployment
Testing Phase
Setting Up Testing Environment
Writing Test Cases
Unit Testing
Integration Testing
System Testing
Functional Testing
Non-Functional Testing
User Interface Testing
Regression Testing
Bug Documentation
Bug Fixing
Final Test Report Writing
User Training
Identifying Training Needs
Developing Training Material
Scheduling Training Sessions
Conducting Training Workshops
Offering Hands-on Training
Demonstrating System Usage
Addressing User Queries
Providing Training Manuals
Conducting Feedback Sessions
Revising Training Content
Post-Training Support
Evaluating Training Effectiveness
System Implementation
Preparing for Deployment
System Configuration
Data Backup
Installing System
Setting User Privileges
Connectivity Checks
Initial System Run
System Monitoring
Addressing Implementation Issues
System Optimization
User Access Provision
Finalizing Implementation Report
Data Migration
Data Migration Planning
Source System Analysis
Data Clean-up
Data Mapping
Preparing Migration Scripts
Test Migration
Data Validation
Resolving Migration Errors
Final Data Migration
Post-Migration Testing
Back-up of Migrated Data
Migration Completion Report
User Acceptance Testing
UAT Planning
UAT Scenario Design
Setting Up UAT Environment
Conducting UAT Briefing
User Test Execution
Capturing User Feedback
Logging Defects
Prioritizing Defects for Fixes
Making Necessary Adjustments
Re-testing After Fixes
Obtaining User Sign-off
Documenting UAT Completion Report
Project Closure
Project Review Meeting
Documenting Lessons Learned
Final Project Report
Project Performance Evaluation
Deliverable Acceptance Confirmation
Release of Project Resources
Archiving Project Documents
Financial Closure
Stakeholder Communication
Feedback Collection
Celebrating Project Completion
Project Closure Report Submission