## Outdoor Billboard Campaig
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=outdoor-billboard-campaign
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Define Project Objective
Identify Stakeholders
Establish Project Team
Develop Project Charter
Determine Success Criteria
Set Project Scope
Assess Risk Factors
Identify Required Resources
Develop Project Timeline
Secure Initial Funds
Implement Project Management Tools
Kick-off Meeting.
Market Research
Define Research Objective
Identify Target Audience
Create Research Design
Select Research Method
Develop Questionnaire
Gather Data
Compile Collected Data
Analyze Data
Interpret Results
Draw Conclusions
Prepare Research Report
Present Findings.
Concept Development
Define Concept Objective
Brainstorm Ideas
Evaluate Ideas
Select Preferred Concept
Develop Detailed Sketch
Create Mock-ups
Test Concept Feasibility
Refine Selected Concept
Secure Concept Approval
Develop Final Concept Document
Prepare Concept Presentation
Present Concept to Stakeholders.
Design Ideation
Understand Design Objective
Review Concept Document
Brainstorm Design Ideas
Sketch Design Proposals
Review Design Sketches
Select Preferred Design
Develop Design Prototype
Revise and Refine Design
Secure Design Approval
Finalize Design Documentation
Prepare Design Presentation
Present Design to Stakeholders.
Content Creation
Define Content Objective
Determine Content Format
Identify Key Messages
Write Initial Copy
Select Visual Elements
Review Initial Content
Edit and Revise Copy
Secure Content Approval
Finalize Visual Elements
Prepare Final Content
Review and Proofread Content
Approve and Finalize Content.
Budget Allocation
Define Budget Objectives
Identify Cost Factors
Estimate Costs
Prioritize Expenditures
Prepare Draft Budget
Review Budget Draft
Make Necessary Adjustments
Finalize Proposed Budget
Secure Budget Approval
Allocate Funds
Monitor Budget Usage
Adjust Budget as Needed.
Billboard Production
Define Production Objectives
Select Production Company
Review Design and Content
Create Production Timeline
Arrange Printing Materials
Start Production Process
Monitor Production Progress
Inspect Quality Control
Finalize Billboard Production
Review Final Product
Approve Final Product
Arrange Product Delivery.
Site Selection
Define Site Criteria
Identify Potential Sites
Evaluate Site Visibility
Assess Traffic Volume
Review Local Regulations
Analyze Cost Factors
Shortlist Potential Sites
Conduct Site Visits
Finalize Site List
Negotiate Site Contracts
Secure Site Permissions
Confirm Site Bookings.
Billboard Installation
Confirm Installation Date
Prepare Installation Team
Check Site Preparedness
Transport Billboard to Site
Review Installation Plan
Begin Installation Process
Monitor Installation Progress
Conduct Quality Checks
Finalize Installation
Clean and Clear Site
Verify Billboard Visibility
Confirm Installation Completion.
Campaign Evaluation
Define Evaluation Criteria
Collect Campaign Data
Analyze Campaign Performance
Measure Audience Engagement
Evaluate Campaign Reach
Assess Impact on Sales
Review Feedback and Comments
Compare with Initial Objectives
Draw Conclusions
Prepare Evaluation Report
Discuss Findings with Team
Present Evaluation to Stakeholders.