## public-park-developmen
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=public-park-development
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Brief Formulation
Stakeholder Identification
Objective Setting
Team Assembly
Budget Estimation
Timeline Creation
Risk Assessment
Resource Planning
Scope Definition
Project Approval Process
Project Plan Creation
Project Kickoff Meeting
Site Assessment
Site Visit Planning
Geographic Analysis
Soil Testing
Environmental Impact Analysis
Accessibility Evaluation
Infrastructure Analysis
Zoning Compliance Check
Landscape Survey
Climate Consideration
Analysis of Potential Hazards
Site Assessment Report Preparation
Site Assessment Review & Approval
Conceptual Design
Research & Inspiration
Preliminary Sketching
Usage Flow Planning
Space Allocation
Theme Development
Material Consideration
Greenery & Landscape Planning
Aesthetic Visualization
Concept Refinement
3D Modeling & Rendering
Conceptual Design Presentation
Feedback & Revision
Public Consultation
Stakeholder Mapping
Consultation Plan Development
Public Notification
Information Package Creation
Public Meeting Scheduling
Conduct Public Meetings
Survey Distribution
Collection of Public Feedback
Analysis of Public Input
Addressing Concerns & Suggestions
Public Consultation Report Preparation
Public Consultation Review & Agreement
Detailed Design
Incorporation of Public Feedback
Detailed Sketching
CAD Model Creation
Structural Designing
Selection of Materials
Landscape Detailing
Lighting Plan Development
Utility Layout Design
Safety Feature Incorporation
Design Documentation
Design Review & Revision
Final Design Approval
Permit Acquisition
Identification of Required Permits
Detailed Review of Permit Regulations
Compilation of Application Documents
Application Preparation
Submission of Initial Applications
Liaison with Regulatory Bodies
Addressing Queries & Concerns
Amendments to Applications (if required)
Resubmission of Revised Applications
Permit Fee Payment
Receipt of Permits
Permit Documentation & Filing
Contractor Selection
Contractor Requirement Definition
Request for Proposal Creation
Proposal Distribution
Contractor Bid Collection
Evaluation of Proposals
Shortlisting of Contractors
Arranging Contractor Interviews
Contract Negotiation
Selection of Winning Bid
Legal Contract Preparation
Contract Execution
Contractor Onboarding
Construction Phase
Construction Kickoff Meeting
Site Preparation
Foundation Laying
Structural Work
Utility Installation
Building Construction
Landscape Construction
Safety & Quality Checks
Problem Resolution
Construction Progress Reporting
Final Inspection
Construction Sign Off
Landscape Installation
Landscape Plan Review
Site Preparation for Landscaping
Soil Enrichment
Installation of Irrigation Systems
Planting Trees & Shrubs
Grass Seeding or Turf Installation
Flower Bed Creation
Installation of Hardscape Elements
Lighting Installation
Landscape Features Addition
Landscape Maintenance Plan Creation
Landscape Project Completion & Review
Project Completion & Review
Final Site Inspection
Snagging List Creation
Remedial Works Completion
Final Documentation Review
Project Handover
Obtaining Client Approval
Project Closure Report Preparation
Lessons Learned Documentation
Team Debrief
Post-Project Evaluation
Public Announcement
Project Celebration