## Public Space Desig
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=public-space-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Conceptualization
Project Briefing
Stakeholder Identification
Objective Setting
Idea Generation
Idea Screening
Feasibility Study
Concept Development
Concept Evaluation
Concept Approval
Documentation
Communication Plan
Transition To Next Phase
Research and Analysis
Data Gathering
Market Analysis
User Behavior Study
Public Space Usage Analysis
Environmental Impact Analysis
Existing Structure Analysis
Comparative Studies
Design Trend Research
Regulatory Requirements Review
Findings Compilation
Report Preparation
Research Presentation
Site Survey
Site Selection
Site Visit Planning
Physical Inspection
Boundary Identification
Topographic Survey
Soil Test
Flora and Fauna Analysis
Climate Study
Noise and Air Quality Measurements
Infrastructure Analysis
Data Analysis and Interpretation
Site Report Compilation
Preliminary Design
Design Brief Review
Initial Sketching
Space Planning
3D Modeling
Material Proposal
Initial Cost Estimation
Design Refinement
Preliminary Design Presentation
Feedback Integration
Design Revisions
Final Preliminary Design Approval
Documentation of Preliminary Design
Detailed Design
Review of Preliminary Design
Detailed Sketching
Advanced 3D Modeling
Detailed Space Layout
Material and Finish Selection
Lighting and Acoustic Plan
Safety and Accessibility Considerations
Detailed Cost Estimation
Design Validation
Detailed Design Presentation
Revisions based on Feedback
Detailed Design Documentation
Material Selection
Material Research
Supplier Identification
Material Sample Collection
Material Testing
Environmental Impact Review
Cost Analysis
Durability Assessment
Aesthetic Evaluation
Material Comparison
Material Selection Decision
Purchase Planning
Material Procurement Schedule.
Cost Estimation
Project Scope Review
Work Breakdown Structure
Material Cost Estimation
Labor Cost Estimation
Equipment Cost Estimation
Overhead Cost Calculation
Contingency Cost Analysis
Total Cost Calculation
Cost Benefit Analysis
Cost Estimation Report Preparation
Cost Estimation Presentation
Cost Estimation Approval.
Approval Procurement
Approval Checklist Preparation
Documentation Compilation
Application Form Filling
Property Rights Verification
Environmental Clearance Application
Building Code Compliance Review
Application Submission
Query Resolution
Approval Status Follow-up
Re-submission (if required)
Approval Receipt
Document Safekeeping
Construction Planning
Construction Strategy Development
Contractor Selection
Work Schedule Creation
Resource Allocation Plan
Safety Plan Development
Quality Assurance Plan
Communication Plan Creation
Risk Management Plan
Budget Review
Timeline Finalization
Construction Plan Approval
Plan Communication to Stakeholders
Project Completion and Review
Completion Checklist Verification
Final Inspection
Punch List Creation
Defect Rectification
Final Quality Check
Documentation Submission
Client Handover
Project Debriefing
Stakeholder Feedback Collection
Project Evaluation
Lessons Learned Documentation
Project Closure Report.