## Raffl
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=raffle
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Raffle Conceptualization
Identifying Purpose
Setting Goals
Determining Budget
Identifying Target Audience
Selecting Raffle Format
Deciding Event Location
Scheduling Date & Time
Legal Considerations Review
Resource Allocation
Strategy Development
Raffle Outline Creation
Project Brief Finalization
Prize Selection
Prize Brainstorming
Budget Evaluation
Prize Category Decision
Vendor Research
Prize Quality Check
Cost Comparison
Prize Relevance Evaluation
Procurement Planning
Approval Process
Order Placement
Delivery Scheduling
Receipt and Storage
Rule Establishment
Preliminary Rule Drafting
Legal Compliance Check
Eligibility Criteria Setting
Ticket Pricing Determination
Winner Selection Methodology
Prize Claim Procedure
Dispute Resolution Method
Draft Revision
Internal Approval Process
External Legal Review
Final Rule Approval
Rule Publication Planning
Marketing Plan
Market Research
Identify Target Audience
SWOT Analysis
Define Marketing Objectives
Select Marketing Channels
Budget Allocation
Create Marketing Message
Plan Marketing Timeline
Design Marketing Materials
Approve Marketing Plan
Execute Marketing Plan
Track and Analyze Results
Ticket Design
Design Brief Creation
Brainstorming Design Ideas
Initial Draft Creation
Incorporate Required Information
Layout and Typography Selection
Color Scheme Decision
Incorporation of Event Branding
Design Revision
Internal Approval
Final Design Approval
File Preparation for Printing
Printing Coordination
Ticket Sales Period
Sales Strategy Planning
Sales Team Training
Ticket Availability Announcement
Sales Kick-off
Regular Sales Monitoring
Customer Service Management
Mid-term Sales Evaluation
Adjustments to Strategy
Promotion Boosting
Final Sales Push
Close of Ticket Sales
Sales Report Generation
Raffle Promotion
Promotion Strategy Planning
Content Creation
Choosing Promotion Channels
Creating a Promotion Calendar
Launching the Initial Promotion
Monitoring Promotion Feedback
Adjusting Promotion Tactics
Engaging with Audience
Running Special Promos or Discounts
Final Promotion Push
Promotion Closeout
Evaluation of Promotion Success
Ticket Collection
Collection Strategy Planning
Setting up Collection Points
Ensuring Secure Collection
Training Collection Staff
Beginning Collection Process
Regular Collection Monitoring
Addressing Collection Issues
Managing Online Ticket Collection
Ensuring Data Privacy
Collection Closing Procedure
Consolidating Collected Tickets
Securely Storing Collected Tickets
Winner Draw
Draw Procedure Planning
Selecting an Neutral Draw Conductor
Preparing Tickets for Draw
Checking the Draw Venue
Setting up Live Broadcast (if applicable)
Final Briefing before Draw
Conducting the Draw
Documenting the Draw Process
Verifying the Ticket of the Winner
Announcing the Winner
Documenting the Winner Details
Post-Draw Clean-up and Review
Prize Distribution
Winner Notification Plan
Verifying Winner's Eligibility
Arranging Winner Announcement
Informing the Winner
Prize Claim Instruction Provision
Winner's Confirmation of Prize Acceptance
Arranging Prize Pick-up or Delivery
Preparing Legal Prize Receipt Documentation
Conducting a Prize Handover Ceremony
Obtaining Signed Prize Receipt
Post-Distribution Follow-up
Documenting Prize Distribution Process