## Residential buildin
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=residential-building-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Briefing
Feasibility Study
Stakeholder Identification
Goals Setting
Budget Estimation
Timeframe Scheduling
Risk Assessment
Resources Planning
Team Formation
Project Kickoff Meeting
Initial Documentation
Approval Procurement
Site Analysis
Site Visit
Topography Study
Soil Analysis
Climate Evaluation
Surrounding Environment Assessment
Accessibility Analysis
Utility Services Review
Legal Constraints Research
Zoning Regulations Study
Site Measurement
Documentation of Site Details
Site Analysis Report Preparation
Design Development
Conceptual Design Creation
Space Planning
Material Selection
Structural Designing
Electrical Layout Planning
Plumbing System Design
HVAC System Design
3D Modeling
Design Revisions
Client Approval
Cost Estimation
Final Design Documentation
Planning Permission
Documentation Preparation
Local Authority Research
Zoning Regulation Compliance Check
Application Form Completion
Submission of Plans
Fee Payment
Public Notification
Addressing Objections
Local Authority Meeting Attendance
Amendments Based on Feedback
Resubmission of Plans (if needed)
Permission Receipt Confirmation
Construction Documents
Detailed Drawings Preparation
Specification Writing
Contract Details Finalization
Material List Creation
Safety Plan Development
Permit Application Incorporation
Construction Schedule Establishment
Cost Estimation Documentation
Quality Control Procedures
Revisions Based on Contractor Feedback
Final Document Review
Construction Documents Submission
Contractor Selection
Contractor Search
Prequalification Screening
Request for Proposal Issuance
Bidding Process Management
Bid Evaluation
Contractor Interviews
Reference Checks
Licensing Verification
Contract Negotiation
Contract Drafting
Contract Review
Contract Signing
Construction Management
Team Briefing
Schedule Monitoring
Quality Control Supervision
Progress Verification
Resource Allocation Management
Subcontractor Coordination
Compliance Enforcement
Problem Resolution
Safety Regulations Monitoring
Status Reporting
Change Orders Management
Record Keeping
Building Construction
Site Prepping
Foundation Construction
Structural Framework Setup
Roofing Installation
Window and Door Fitting
Electrical and Plumbing Installation
HVAC Installation
Insulation and Drywall Installation
Interior Finishing
Exterior Finishing
Landscaping
Final Inspection
Quality Assurance
Quality Standards Review
Quality Control Plan Implementation
Regular Site Inspections
Materials Quality Testing
Workmanship Evaluation
Compliance Checks
Progress Reporting
Issue Identification
Corrective Actions Planning
Quality Re-inspections
Root Cause Analysis
Continuous Improvement Actions
Project Handover
Completion Confirmation
Final Inspection Arrangement
Snagging List Creation
Rectification of Snags
Final Clean-up
Handover Document Preparation
Client Walkthrough
Training on Building Operations
Handover Document Submission
Keys Handover
Final Payment Processing
Post-Project Review.