## residential-garden-desig
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=residential-garden-design
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Initial Consultation
Appointment Scheduling
Client Briefing
Project Objectives Discussion
Style Preferences Exploration
Budget Scope Determination
Timeframe Agreement
Site Visit Arrangement
Existing Plans Review
Potential Challenges Identification
Preliminary Ideas Presentation
Client Feedback Collection
Consultation Summary Report
Site Assessment
Site Visit
Boundary Measurement
Soil Analysis
Climate Evaluation
Sunlight Tracking
Vegetation Survey
Prevailing Wind Assessment
Drainage Inspection
Access Points Identification
View Vantage Points Analysis
Existing Structures Evaluation
Site Assessment Report
Concept Development
Research and Inspiration
Sketching Initial Ideas
Space Zoning
Planting Scheme Drafting
Features and Structures Brainstorming
Lighting Plan Outlining
Material Palette Development
Mood Board Creation
3D Visual Mockup Design
Sustainability Considerations
Review with Client
Concept Refinement and Finalization
Design Approval
Preparation of Presentation
Arrangement of Meeting
Presentation of Concept Design
Walkthrough of Design Elements
Explanation of Material Choices
Presentation of Project Timeline
Budget and Cost Discussion
Addressing Client Concerns
Incorporation of Client Feedback
Revision of Design Proposal
Final Approval Request
Agreement Sign-off
Material Selection
Research on Materials
Consideration of Aesthetics
Durability Evaluation
Budget Implication Analysis
Environmental Impact Assessment
Supplier Identification
Material Samples Collection
Review of Samples with Client
Selection of Primary Materials
Selection of Secondary Materials
Confirmation of Material Choices
Order Placement
Budget Estimation
Itemized Cost Breakdown
Material Costs Estimation
Labor Costs Projection
Equipment Rental Fees Assessment
Transportation Costs Calculation
Contingency Fund Allocation
Tax and Duties Consideration
Potential Additional Costs Analysis
Profit Margin Addition
Total Budget Compilation
Client Budget Presentation
Budget Approval and Sign-off
Detailed Design
Detailed Measurements Recording
Creation of Scale Drawings
Elevation Plans Development
Specification Sheets Preparation
Plant Placement Design
Lighting Plan Detailing
Irrigation System Design
Drainage System Detailing
Construction Detail Drawings
Review and Amendments
Final Design Documentation
Client Presentation and Approval
Construction Planning
Contractor Selection
Project Timeline Creation
Permit Applications
Safety Measures Planning
Equipment and Material Scheduling
Workforce Allocation
Sequence of Work Establishing
Site Preparation Planning
Waste Management Strategy
On-site Meeting Arrangement
Contingency Planning
Final Construction Plan Approval
Implementation
Site Preparation
Material Delivery
Groundwork and Excavation
Foundation and Structure Construction
Installation of Hardscaping
Drainage and Irrigation Installation
Planting and Landscaping
Lighting Installation
Installation of Additional Features
Cleanup and Waste Removal
Final Inspection
Client Walkthrough and Handover
Maintenance Plan
Assessment of Garden Requirements
Creation of Task List
Watering Schedule Development
Fertilizing Plan Creation
Pruning and Trimming Schedule
Pest and Disease Management Plan
Seasonal Maintenance Outline
Lawn Care Program
Replacement and Upkeep Plan
Waste Disposal Guidelines
Maintenance Plan Documentation
Plan Review with Client