## school-playground-constructio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=school-playground-construction
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Planning
Project Kick-Off
Stakeholder Identification
Scope Definition
Objective Setting
Risk Assessment
Task Delegation
Resource Allocation
Timeline Creation
Communication Plan Development
Contingency Planning
Project Charter Creation
Project Plan Approval
Site Inspection
Site Identification
Preliminary Site Visit
Site Documentation
Environmental Assessment
Soil Testing
Terrain Evaluation
Site Measurement
Infrastructure Evaluation
Potential Hazard Identification
Accessibility Assessment
Site Inspection Report Compilation
Inspection Review & Approval
Design Drafting
Conceptualization
User Requirement Gathering
Playground Equipment Selection
Layout Sketching
Materials Specification
Safety Feature Planning
3D Modeling
Accessibility Design
Environmental Impact Assessment
Design Review and Feedback
Design Revisions
Final Design Approval
Budgeting & Funding
Cost Estimation
Detailed Budget Development
Funding Source Identification
Funding Application Preparation
Funding Submission
Income Projection
Expense Analysis
Budget Review & Adjustment
Funding Approval Waiting
Budget Approval
Fund Allocation
Financial Plan Finalization
Regulatory Approval
Researching Regulations
Preparing Compliance Document
Reviewing Safety Standards
Application Preparation
Application Submission
Liaising with Regulatory Bodies
Responding to Queries
Revising Application if Needed
Awaiting Decision
Receiving Approval or Denial
Addressing Required Changes
Securing Final Approval
Procurement of Materials
Material Needs Identification
Supplier Research
Request for Quotations
Bid Evaluation
Supplier Selection
Contract Negotiation
Procurement Order Placement
Order Confirmation
Delivery Schedule Agreement
Receiving & Checking Materials
Quality Inspection
Stock and Store Materials
Construction Initiation
Kick-off Meeting
Site Preparation
Equipment Mobilization
Safety Briefing
Task Scheduling
Labor Assignment
Construction Process Initiation
Regular Progress Monitoring
Problem Identification
Solution Implementation
Quality Control Checks
Phase Completion Verification
Playground Installation
Equipment Positioning
Groundwork Construction
Equipment Assembly
Equipment Installation
Safety Surface Installation
Landscape Development
Accessibility Feature Implementation
Aesthetic Enhancements
Waste Management
Installation Quality Check
Minor Adjustments
Installation Completion Confirmation
Safety Inspection
Pre-Inspection Checklist Creation
Inspection Scheduling
Conducting Initial Inspection
Equipment Safety Check
Surface Safety Evaluation
Accessibility Feature Verification
Hazard Identification
Risk Assessment
Safety Report Generation
Safety Improvement Recommendations
Implementing Safety Measures
Final Safety Approval
Project Completion & Handover
Completion Verification
Final Quality Control Check
Documentation Compilation
Project Report Generation
Final Financial Audit
Project Review & Lessons Learned
Preparation of Handover Documents
Handover Briefing Preparation
Conducting Handover Briefing
Handing Over the Project
Post-Handover Support Planning
Project Closure