## Series A funding roun
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=series-a-round
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Market Research
Define Objectives
Identify Target Market
Research Industry Trends
Competitor Analysis
Consumer Behavior Analysis
Product/Service Analysis
Data Collection Design
Field Work or Data Collection
Data Analysis
Interpret Findings
Report Preparation
Review and Adjust Strategy Based on Findings
Business Plan Creation
Vision and Mission Definition
Identify Key Business Goals
Market Analysis Synthesis
Organizational Structure Development
Product/Service Line Definition
Marketing and Sales Strategy Formulation
Operations Plan Development
Financial Projection Calculation
Executive Summary Writing
Business Plan Review
Fine-tuning and Revisions
Final Business Plan Compilation
Prototype Development
Conceptualize Idea
Sketch Design
Develop Specifications
Create 3D Rendering
Build Physical Model
Initial Testing
Analyze Test Results
Refine Design
Build Revised Prototype
Conduct Final Testing
Analyze Final Test Results
Finalize Prototype Design
Team Assembly
Identify Team Roles
Define Job Descriptions
Post Job Advertisements
Screen Applications
Conduct Interviews
Check References
Select Team Members
Offer Positions
Conduct Onboarding
Define Team Responsibilities
Organize Team Building Activities
Establish Performance Review Process
Networking and Outreach
Identify Target Contacts
Develop Network Strategy
Attend Industry Events
Create Social Media Presence
Join Professional Associations
Host Networking Events
Engage in Online Forums
Follow-up on Contacts
Build Partnership Opportunities
Seek Advice from Mentors
Maintain Regular Communication
Evaluate Network Effectiveness
Investment Deck Preparation
Identify Presentation Goals
Gather Relevant Information
Market Research Summary
Draft Business Model Overview
Outline Marketing Strategy
Detail Financial Projections
Develop Team Profile
Create Investment Proposal
Design Presentation Layout
Review and Revise Content
Practice Pitch Delivery
Finalize Investment Deck
Pitching to Investors
Identify Potential Investors
Establish Contact
Schedule Meetings
Prepare Presentation
Conduct Rehearsals
Finalize Presentation Details
Present the Pitch
Address Investor Queries
Gather Feedback
Follow-up Meetings
Modify Pitch Based on Feedback
Establish Negotiation Plan
Negotiation
Analyze Investor Proposal
Define Negotiation Objectives
Prepare Counter Proposal
Select Negotiation Team
Conduct Mock Negotiation Sessions
Attend Negotiation Meetings
Present Counter Proposal
Address Concerns and Queries
Propose Revisions if Necessary
Agree on Final Terms
Legal Review of Agreement
Sign Investment Deal
Funding Acquisition
Finalize Funding Agreement
Arrange Legal Documentation
Review Terms and Conditions
Sign Funding Agreement
Organize Funds Transfer
Confirm Receipt of Funds
Update Business Plan with Funding Details
Communicate Funding Success to Team
Inform Stakeholders
Adjust Financial Projections
Review and Update Budgets
Start Deployment of Funds
Post-Funding Strategy Execution
Review Business Strategy
Update Goals and Objectives
Allocate Resources
Implement Marketing Plan
Commence Sales Strategy
Monitor Performance Metrics
Regular Investor Communication
Adapt Strategy Based on Performance
Staff Training and Development
Explore Additional Revenue Streams
Community and Customer Engagement
Continued Business Growth Evaluation