## Server Upgrad
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=server-upgrade
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Kick-off Meeting
Stakeholder Identification
Project Scope Definition
Project Objectives Setting
Risk Assessment
Team Assembling
Roles and Responsibilities Allocation
Communication Plan Creation
Project Schedule Drafting
Resource Planning
Budget Estimation
Project Charter Preparation
Requirements Gatheirng
Identify Key Stakeholders
Plan Requirement Gathering Sessions
Conduct Interviews
Organize Brainstorming Sessions
Facilitate Workshops
Execute Surveys and Questionnaires
Analyze Existing System Documentation
Document Use Cases
Prioritize and Rank Requirements
Validate Requirements with Stakeholders
Requirements Documentation
Obtain Requirements Approval
Server Assessment
Define Assessment Objectives
Review Current Server Infrastructure
Evaluate Server Performance
Conduct Capacity Analysis
Assess Security Measures
Analyze System Vulnerabilities
Audit Data Integrity
Perform Hardware Inspection
Assess Software Compatibility
Review Backup and Recovery Procedures
Document Assessment Findings
Present Assessment Report
Budgeting & Planning
Identify Financial Objectives
Review Project Scope
Estimate Resource Costs
Forecast Server Equipment Costs
Calculate Labor Expenses
Include Contingency Funds
Analyze Financial Risks
Validate Budget with Stakeholders
Prepare Budget Document
Establish Project Timeline
Allocate Resources per Activity
Finalize and Approve Project Plan
Procurement of Resources
Identify Necessary Resources
Develop Procurement Plan
Source Potential Suppliers
Request Quotations
Evaluate Supplier Offers
Negotiate Contract Terms
Finalize Supplier Selection
Issue Purchase Orders
Handle Delivery Schedules
Receive and Inspect Resources
Secure Storage of Resources
Inventory Management and Record Keeping
Server Installation
Prepare Installation Environment
Unpack Server Equipment
Position and Secure Equipment
Connect Hardware Components
Power On and Inspect Hardware
Install Operating System
Configure Server Settings
Install and Update Required Software
Setup Network Connections
Configure Security Settings
Run Initial System Checks
Document Installation Process
Data Migration
Data Migration Planning
Identify Data to Migrate
Create Data Backup
Perform Data Cleaning
Develop Migration Strategy
Prepare Target Server
Test Migration Process
Execute Data Migration
Verify and Validate Migrated Data
Resolve Migration Issues
Final Data Sync
Decommission Old Server
Testing & Validation
Develop Testing Strategy
Create Test Cases
Prepare Testing Environment
Execute Functionality Testing
Perform Load and Stress Testing
Conduct Security Testing
Run Performance Testing
Validate Data Integrity
Analyze Test Results
Resolve Identified Issues
Retest Fixed Issues
Generate Test Summary Report
Server Deployment
Develop Deployment Plan
Prepare Production Environment
Conduct Final System Review
Schedule Deployment Time
Notify Stakeholders
Execute Server Deployment
Monitor System Performance
Validate Operational Requirements
Conduct User Training
Transition to Operational Team
Address Post-deployment Issues
Document Deployment Process
Post-upgrade Review
Gather Project Documents
Solicit Feedback from Stakeholders
Evaluate Project Performance
Analyze Budget Variance
Review Project Deliverables
Assess Server Performance Post Upgrade
Document Lessons Learned
Prepare Post-upgrade Report
Present Findings to Stakeholders
Update Project Management Practices
Archive Project Information
Celebrate Project Completion