## Silent Auctio
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=silent-auction
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Brief Preparation
Project Objective Setting
Stakeholder Identification
Project Team Formation
Define Responsibilities
Project Schedule Creation
Risk Assessment
Project Charter Development
Initial Budget Estimation
Approval Seek
Communication Plan Development
Project Kickoff Meeting
Budget Planning
Financial Objective Identification
Revenue Forecasting
Expense Estimation
Cost of Auction Items
Venue Cost Calculation
Marketing Cost Evaluation
Staffing Cost Assessment
Budget Drafting
Budget Review
Budget Revision
Budget Finalization
Budget Approval Process
Auction Item Procurement
Item Requirement Definition
Potential Donor Identification
Donation Request Letter Preparation
Letter Distribution
Donor Follow-Up
Donation Confirmation
Item Collection Arrangement
Item Verification
Donation Acknowledgement
Item Cataloging
Item Storage Arrangement
Pre-auction Item Display Setup
Event Promotion
Promotion Strategy Development
Target Audience Identification
Marketing Material Design
Website Update
Social Media Campaign Launch
Press Release Writing
Media Partnership Establishment
Email Marketing Launch
Direct Mail Campaign Execution
Local Community Outreach
VIP Invitation Send-out
Promotion Tracking and Adjustment
Venue Selection
Venue Requirement Assessment
Potential Venue Research
Site Visits Arrangement
Venue Capacity Evaluation
Accessibility Check
Facility Availability Assessment
Cost Analysis
Venue Booking Inquiry
Contract Review
Deposit Arrangement
Venue Booking Confirmation
Venue Layout Planning
Auction Software Setup
Software Needs Identification
Auction Software Research
Software Shortlisting
Vendor Communication
Software Demo Scheduling
Software Selection
Software Purchase
Software Installation
Data Input
Software Customization
Testing & Validation
Live Software Deployment
Staff and Volunteer Training
Training Needs Assessment
Training Content Development
Training Schedule Preparation
Trainer Identification
Training Materials Preparation
Training Invitations Sending
Introduction to Auction Procedures
Auction Software Training
Customer Relations Briefing
Emergency Procedures Training
Mock Auction Conducting
Training Feedback Collection
Event Execution
Venue Preparation
Staff Briefing
Volunteer Coordination
Vendor Management
Guest Registration
Silent Auction Opening
Ongoing Event Monitoring
Troubleshooting
Bid Collection
Winner Announcement
Auction Closeout
Event Wrap-up
Post-Event Analysis
Initial Debriefing
Data Collection
Financial Reconciliation
Event Feedback Collection
Feedback Review
Performance Analysis
Event Outcome Evaluation
Lessons Learned Identification
Suggestions for Improvements
Final Report Preparation
Stakeholder Presentation
Documentation Archiving
Project Closure
Project Completion Verification
Outstanding Tasks Resolution
Financial Settlement
Resource Release
Auction Item Return (if applicable)
Project Documentation Finalization
Project Evaluation
Team Debriefing
Project Success Celebration
Stakeholder Communication
Project Closure Report
Project Archive and Backup