## Small wedding (15 guests max
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=small-wedding
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Guest List Compilation
Brainstorm Potential Guests
Consult with Partner
Identify Priorities
Finalize Primary List
Prepare Back-up List
Collect Contact Information
Verify Contact Details
Address Special Requirements
Allocate Seating Arrangements
Share List with Venue
Final Guest Confirmation
Prepare for Guest Arrival
Venue Selection
Define Venue Criteria
Research Potential Venues
Visit Venue Websites
Compile Venue Shortlist
Schedule Venue Visits
Conduct Venue Visits
Evaluate Venue Facilities
Compare Venue Costs
Negotiate Venue Contract
Confirm Venue Booking
Inform Guests of Venue
Plan Venue Layout
Invitation Designing
Determine Invitation Style
Research Design Ideas
Sketch Preliminary Designs
Select Invitation Materials
Finalize Design Concept
Confirm Invitation Wording
Hire Professional Designer
Review Design Proofs
Make Design Adjustments
Approve Final Design
Print Invitations
Prepare Invitations for Mailing
Catering Arrangements
Define Menu Preferences
Research Catering Services
Accumulate Caterer Shortlist
Arrange Caterer Meetings
Conduct Caterer Interviews
Request Sample Menus
Schedule Food Tastings
Discuss Dietary Restrictions
Finalize Menu Selections
Negotiate Catering Contract
Confirm Catering Booking
Coordinate Catering Schedule
Decoration Planning
Establish Decor Theme
Collect Decor Inspirations
Identify Decor Elements
Source Decor Suppliers
Conduct Supplier Meetings
Choose Decor Items
Create Decor Layout
Confirm Decor Costs
Finalize Decor Orders
Schedule Decor Delivery
Coordinate Decor Setup
Plan Decor Breakdown
Dress and Attire Selection
Define Dress Style
Research Dress Designers
Schedule Dress Fittings
Try on Various Designs
Select Wedding Dress
Arrange Dress Alterations
Finalize Dress Accessories
Select Groom's Attire
Schedule Groom's Fittings
Finalize Groom's Accessories
Plan Guests' Dress Code
Organize Dress Delivery
Entertainment Booking
Identify Entertainment Preferences
Research Entertainment Options
Compile Entertainer Shortlist
Schedule Entertainer Meetings
Attend Performance Samples
Discuss Performance Requirements
Select Entertainers
Negotiate Entertainment Contracts
Confirm Entertainer Bookings
Plan Entertainment Schedule
Coordinate Entertainer Setup
Arrange Entertainer Payments
Rehearsal Planning
Define Rehearsal Objectives
Schedule Rehearsal Date
Choose Rehearsal Venue
Plan Rehearsal Program
Assign Rehearsal Roles
Communicate Rehearsal Details
Confirm Rehearsal Attendees
Prepare Rehearsal Materials
Conduct Rehearsal Walkthrough
Review Rehearsal Feedback
Make Rehearsal Adjustments
Finalize Rehearsal Plans
Wedding Ceremony Execution
Prepare Venue Setup
Coordinate Vendor Arrivals
Setup Decorations
Confirm Guest Arrivals
Manage Ceremony Music
Coordinate Bridal Procession
Conduct Wedding Ceremony
Facilitate Vows Exchange
Oversee Ring Exchange
Manage Document Signing
Coordinate Recessional
Transition to Reception
Post-Wedding Reception.
Prepare Reception Setup
Manage Guest Transition
Coordinate Reception Music
Initiate Reception Program
Facilitate Speeches and Toasts
Serve Wedding Meal
Initiate Dance Floor
Cut Wedding Cake
Distribute Wedding Favors
Coordinate Guest Departures
Manage Reception Clean-Up
Handle Vendor Payments