## Social Media Campaig
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=social-media-campaign
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Briefing
Objectives Definition
Stakeholder Identification
Resource Inventory
Project Scope Outline
Budget Estimation
Risk Assessment
Project Timeline Creation
Team Formation
Communication Plan Development
Approval Process Setup
Project Kickoff Meeting
Market Research
Defining Research Goals
Identifying Target Audience
Competitor Analysis
Market Trend Identification
Survey Design
Field Research
Online Data Gathering
Social Media Analysis
Data Validation
Data Interpretation
Market Insight Synthesis
Research Report Creation
Content Strategy Development
Content Goals Identification
Audience Persona Creation
Platform Selection
Content Type Definition
Content Topic Brainstorming
Keyword Research
Editorial Calendar Creation
Content Creation Guidelines
Content Promotion Plan
SEO Strategy Formation
Content Measurement Metrics
Strategy Documentation
Campaign Designing
Campaign Goal Formulation
Campaign Theme Ideation
Visual Style Development
Copywriting Brief Creation
Landing Page Designing
Ad Design Creation
User Journey Mapping
Call-to-Action Planning
Mobile Responsiveness Check
User Testing Sessions
Feedback Incorporation
Final Campaign Approval
Team Assignment
Team Structure Planning
Role Definition
Skill Inventory
Resource Allocation
Team Member Selection
Task Assignment
Team Briefing
Training Sessions (if required)
Tool Setup
Progress Tracking Mechanism
Communication Channels Establishment
Conflict Resolution Procedures
Content Creation
Content Brief Review
Content Research
Copywriting
Graphic Designing
Video Production (if applicable)
Infographic Creation (if applicable)
Content Review Round
SEO Optimization
Proofreading and Editing
Legal Review (for compliance)
Final Content Approval
Content Scheduling
Campaign Launch
Pre-Launch Checklist Review
Internal Communication
Landing Page Setup
Social Media Post Scheduling
Email Campaign Setup
Paid Advertising Activation
Influencer Outreach
Press Release Distribution
Launch Announcement
User Engagement Monitoring
Quick Fixes and Adjustments
Launch Day Report Generation
Social Media Monitoring
Monitoring Tools Setup
Key Metrics Identification
Social Media Channels Tracking
User Engagement Analysis
Sentiment Analysis
Competitor Performance Monitoring
Crisis Alert Setup
Influencer Tracking
Content Performance Review
Audience Feedback Collection
Daily Monitoring Report
Data Interpretation and Insights
Performance Analysis
Data Collection
Data Sorting
Key Performance Indicators Measurement
Trend Identification
Conversion Analysis
Engagement Metrics Analysis
ROI Calculation
A/B Testing Analysis
Channel-Specific Analysis
User Feedback Review
Performance Report Preparation
Insights and Recommendations Drafting
Post-Campaign Review
Data Aggregation
Comprehensive Analysis
Goal Achievement Review
Lessons Learned Identification
Successes and Failures Evaluation
Audience Feedback Analysis
Cost Effectiveness Evaluation
Team Performance Review
Improvement Areas Identification
Best Practices Documentation
Post-Campaign Report Preparation
Stakeholder Presentation and Feedback