## Social Media Identit
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=social-media-identity
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initiation
Project Kick-off
Objective Definition
Team Assembling
Stakeholder Identification
Resource Allocation
Budget Estimation
Project Schedule Creation
Risk Assessment
Communication Plan Development
Quality Assurance Plan
Documentation Preparation
Project Approval
Market Research
Identify Research Goals
Select Research Methods
Define Target Audience
Collect Industry Information
Conduct Competitive Analysis
Perform Customer Surveys
Analyze Social Media Trends
Evaluate Market Potential
Synthesize Data Gathered
Assess Market Opportunities
Prepare Research Report
Present Research Findings
Conceptualization
Brainstorming Session
Idea Generation
Concept Development
Concept Evaluation
Identify Unique Selling Proposition
Visual Identity Creation
Messaging Development
Brand Voice Determination
Drafting Strategic Approach
Feedback Collection
Concept Refinement
Concept Finalization
Design Development
Design Brief Creation
Sketching Ideas
Layout Drafting
Typography Selection
Color Palette Choice
Visual Elements Creation
Mockup Development
User Interface Design
User Experience Design
Prototype Creation
Design Review
Design Finalization
Content Creation
Content Strategy Development
Keyword Research
Topic Generation
Content Calendar Creation
Writing First Drafts
Graphics & Media Production
Content Editing
SEO Optimization
Content Formatting
Content Approval
Content Scheduling
Content Publishing
Platform Selection
Identify Potential Platforms
Analyze Platform Demographics
Evaluate Platform Features
Assess Platform Usability
Review Platform Cost
Platform Compatibility Check
Conduct Platform Testing
Analyze Platform Performance
Compare Platform Pros and Cons
Decide on Primary Platform
Select Secondary Platforms
Confirm Platform Selection
Identity Integration
Platform Profile Setup
Logo and Visuals Upload
Brand Bio Writing
Contact Information Integration
Theme and Color Scheme Application
Brand Messaging Insertion
Website Linking
Social Network Linking
Content Upload
Platform Customization
Brand Identity Review
Brand Identity Launch
Testing Phase
Develop Testing Criteria
User Interface Testing
User Experience Testing
Content Review
Functionality Testing
Compatibility Testing
Performance Testing
Security Testing
Feedback Collection
Issue Identification
Problem Resolution
Retesting and Validation
Project Launch
Final Preparations
Launch Strategy Development
Launch Timeline Creation
Promotion Plan Development
Press Release Writing
Scheduling Posts
Launch Event Planning
Stakeholder Notifications
Live Deployment
Launch Event Execution
Post-launch Promotion
Launch Evaluation
Review and Improve
Post-launch Feedback Collection
Data Analysis
Performance Evaluation
Identify Improvement Areas
Develop Improvement Plan
Implement Changes
User Experience Re-testing
Measure Impact of Changes
Refine Strategy
Continuous Improvement Plan
Regular Performance Review
Ongoing Optimization