## studio-portrait
Excel is far from ideal for creating and managing Gantt charts. As an alternative we have built Tom's Planner. And we would like to invite you to give it a try at:
https://plan.tomsplanner.com/?template=studio-portraits
You can sign up for a free account and immediately continue with this template.
weeks/days: |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
activity: | resource: | status:
Project Initialization
Project Definition
Objective Setting
Establishing Team Roles
Resource Allocation
Budget Planning
Timeline Development
Risk Assessment
Procurement Planning
Communication Plan Development
Quality Assurance Planning
Documentation Preparation
Project Kick-off Meeting
Influencer Selection
Market Research
Influencer Criteria Definition
Potential Influencer Identification
Social Media Analysis
Influencer Shortlisting
Outreach Strategy Development
Initial Contact
Influencer Interviewing
Contract Negotiation
Selection Decision
Influencer Onboarding
Public Announcement
Content Strategy Development
Audience Analysis
Goal Setting
Content Type Identification
Content Theme Planning
Keyword Research
Competitor Content Analysis
Content Calendar Creation
Resource Allocation
Content Briefing
Approval Process Setup
Distribution Channel Selection
Strategy Finalization
Pre-production Planning
Script Development
Storyboarding
Location Selection
Casting (if applicable)
Schedule Finalization
Equipment Reservations
Wardrobe and Props Planning
Legal Documentation
Logistics Arrangements
Staff Briefing
Rehearsals
Pre-production Meeting
Shoot Location Scouting
Initial Research
Budget Consideration
Potential Location Identification
Visit Scheduling
Location Visiting
Location Evaluation
Safety Assessment
Lighting Test
Sound Test
Accessibility Review
Location Shortlisting
Final Location Approval
Content Creation & Shooting
Crew Assembly
Equipment Setup
Scene Preparation
Makeup and Styling
Camera Positioning
Lighting Adjustment
Sound Check
Rehearsal Take
Actual Shooting
Review Footage
Reshoots (if needed)
Wrap-up & Equipment Dismantling
Post-production Editing
Footage Review
Selection of Clips
Video Assembly
Sound Editing
Color Correction
Visual Effects Addition
Titles and Graphics Incorporation
First Edit Review
Revision and Finalization
Format Conversion
Quality Check
Final Edit Approval
Marketing Strategy Formulation
Market Analysis
Competitor Research
Target Audience Identification
Marketing Objectives Definition
Marketing Channels Selection
Content Planning
Budget Allocation
Promotion Tactics
Partnership Opportunities Exploration
Marketing Timeline Creation
Strategy Review and Approval
Marketing Plan Documentation
Social Media Release
Final Content Review
Release Date Confirmation
Platform Formatting
Caption Creation
Hashtag Research
Scheduling Posts
Audience Engagement Plan
Cross-Promotion Coordination
Content Upload
Release Announcement
Audience Interaction
Post-release Analysis
Performance Evaluation & Reporting
Data Collection
KPI Identification
Audience Engagement Analysis
Reach Reporting
Content Performance Review
Conversion Rate Calculation
ROI Calculation
Influencer Performance Evaluation
Feedback Gathering
Report Compilation
Key Insights Identification
Presentation of Final Report